| Jun 5 | LIAB Mtg. WIS Phase 2 Presentation June 7 San Fran |  | Decision in R.98-09-005 June 8??? Party Comments on LIAB’s PY 2001 Submital June 5 |  | WIS Phase 2 Meeting June 8 San Fran LIAB Comments on WIS Phase 1 June 9 Party Comments on WIS Phase 1 June 9 RRM and Admin Costs Working Group Meetings??? |  |  | Review Invoices and Expenses Web Site Updates Draft Minutes Update Critical Path LIAB’s Bylaws For Public Comment June 1??? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Jun 12 |  |  | LIAB Reply Comments on LIAB’s PY 2001 Submittal June 12 | Update Penetration Rate Table Review Program Expenditures | WIS Phase 2 Meeting Los Angeles June 13 RRM and Admin Costs Working Group Meetings?? |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Fin Tracking |
| Jun 19 | LIAB TC Mtg. WIS Phase 2 Presentation June 20&21 San Fran |  |  |  | Reply Comments on WIS Phase 1 June 19 WIS Phase 2 Meeting San Fran June 22 RRM and Admin Costs Working Group Meetings??? |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Draft Minutes |
| Jun 26 | LIAB Mtg. Budget Review?? June 27&28 Sacramento | Draft Needs Assessment Workplan June 30 |  |  | RRM and Admin Costs Working Group Meetings??? |  |  | Review Invoices and Expenses Web Site Updates Draft Minutes Define Support Tasks for July Update Critical Path Comments on LIAB Draft Bylaws June 30??? Comments on LIAB Draft Bylaws June 30??? |
| Jul 3 |  |  |  |  | WIS Phase 2 Meeting San Fran July 6 RRM and Admin Costs Working Group Meetings?? |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Solicitation of Candidates for LIAB July - Aug |
| Jul 10 | LIAB Mtg Jul 10&11 San Fran |  |  | Update Penetration Rate Table Review Program Expenditures | RRM and Admin Costs Working Group Meetings?? |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Draft Minutes Fin Tracking |
| Jul 17 |  |  |  |  | WIS Phase 2 Meeting San Fran July 19 RRM and Admin Costs Working Group Meetings?? |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |
| Jul 24 | TC Mtg (WIS P 2 Presentation July 26) Jul25&26 LA | Final Workplan July 30 |  |  | WIS Phase 2 Meeting Los Angeles July 27 RRM and Admin Costs Working Group Meetings?? |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |
| Jul 31 | LIAB Mtg Finalize Budget (WIS P 2 PresentationAug 2) Aug 1&2 SF |  |  |  | RRM and Admin Costs Working Group Meetings?? |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Draft Minutes |
| Aug 7 |  |  |  | Update Penetration Rate Table Review Program Expenditures | WIS Draft Phase 2 Rpt Aug 7 RRM and Admin Costs Working Group Meetings?? |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |
| Aug 14 | TC Mtg Aug 15&16 San Diego |  |  |  | RRM and Admin Costs Working Group Meetings?? |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Fin Tracking |
| Aug 21 |  |  |  |  | WIS Phase 2 Meeting San Diego Aug 22 RRM and Admin Costs Working Group Meetings?? |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |
| Aug 28 | LIAB Mtg (WIS P2 PresentationAug 29) Aug 29&30 LA | RFP Issued Aug 29?? | Utility Compliance Filing Sept 1 |  | WIS Phase2 Report Sept 1 RRM and Admin Costs Working Group Meetings Joint Utility Proposal on Standardization (Phase II) Sep 1 |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path LIAB Budget Submittal Sept 1 Submit LIAB Nominations for LIAB 2001 Sept 1 Draft Minutes |
| Sep 4 |  |  |  |  |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |
| Sep 11 | TC Mtg Sep 12&13 San Fran |  |  | Update Penetration Rate Table Review Program Expenditures |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Fin Tracking Draft Minutes |
| Sep 18 | LIAB Mtg Sep 19&20 Monterey |  |  |  |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Draft Minutes |
| Sep 25 |  |  |  |  | LIAB Comments on WIS Phase 2 Sept 30?? Comments on WIS Phase 2 Sept 30?? Report on RRM2 & Admin Costs Oct 1 |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Comments on LIAB Budget Oct 1 |
| Oct 2 | TC Mtg Oct3&4 Sacramento |  |  |  |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |
| Oct 9 |  |  |  | Update Penetration Rate Table Review Program Expenditures |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Fin Tracking |
| Oct 16 | LIAB Mtg Oct 17&18 Fresno |  |  |  | Comments on RRM2 & Admin Oct 21 Comments on RRM2 & Admin Oct 21 |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Draft Minutes |
| Oct 23 |  | P 1 Consultant Selected Oct 28?? |  |  |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |
| Oct 30 | TC Mtg Nov 1&2 LA |  |  |  | Reply Comments on RRM2 Nov 5 |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |
| Nov 6 |  | Consultant Begins Work Nov 7? |  | Update Penetration Rate Table Review Program Expenditures |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Fin Tracking |
| Nov 13 | LIAB Mtg Nov 14&15 San Fran |  |  |  |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Draft Minutes |
| Nov 20 |  |  |  |  |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |
| Nov 27 | TC Mtg Nov 28&29 San Fran |  |  |  | Utility Feedback on Draft manuals Dec 1 |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Draft Minutes |
| Dec 4 |  |  |  |  |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |
| Dec 11 | LIAB Mtg Dec 12 &13 San Fran |  |  | Update Penetration Rate Table Review Program Expenditures | Revised Manuals Dec 15 |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path Draft Minutes Fin Tracking |
| Dec 18 | TC Mtg Dec 19&20 San Diego |  |  |  |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |
| Dec 25 |  |  |  |  |  |  |  | Review Invoices and Expenses Web Site Updates Update Critical Path |