Low Income Program Schedule

May 30, 2000 Through July 31, 2001 (6)

| Task | Authority | Group | Date |
| --- | --- | --- | --- |
| Needs Assessment Workshop | E-3646 | CPUC | May 30-31 |
| Utility Outreach Pilot Programs Begin |  | Utilities | June 1 |
| LIAB Bylaws Distributed |  | CPUC | June 1 |
| Advice Letter Filing on Income Guidelines |  | Utilities | May 24 |
| WIS Project Meeting: CO Monitoring/CAS Testing | (3) | WIS | June 2 |
| Determine Data Gathering and Reporting for Outreach Pilots |  | Energy/Utilities | June |
| RRM &Admin Costs Working Group Meetings | (4) | WG | June through September |
| Party Comments on LIAB PY 2001 Submittal | (3) | Parties | June 5 |
| LIAB Meeting – San Francisco |  | LIAB | June 7 |
| WIS Presentation- LIAB Meeting | (3) | WIS | June 7 |
| WIS Project Meeting: General P&P and/or CO/CAS Cleanup (San Francisco) | (3) | WIS | June 8 |
| LIAB Filing on WIS PHASE 1 | (3) | LIAB | June 9 |
| Party Comments on WIS Phase 1 | (3) | Parties | June 9 |
| National Low-Income Program Conference (Los Angeles) |  |  | June 12-16 |
| LIAB Reply On PY 2001 Recommendations | (3) | LIAB | June 12 |
| WIS Project Meeting: General P&P (Los Angeles) | (3) | WIS | June13 |
| Reply Comments on WIS Phase 1 | (3) | Utilities | June 19 |
| LIAB TC Meeting – San Francisco |  | TC | June 20-21 |
| WIS Presentation-TC Meeting | (3) | WIS | June 21 |
| WIS Project Meeting: General P&P (incl. Co/CAS) (San Francisco) | (3) | WIS | June 22 |
| LIAB Meeting – Sacramento |  | LIAB | June 27 & 28 |
| Public Comments on LIAB Bylaws |  | Parties | June 30 |
| Draft Needs Assessment Workplan | E-3646 | Energy | June 30 |
| Utilities, with Energy Division, to develop Proposal to Standardize Data on Bill Savings and Expenditures for LIEE on Overall and Per Unit Basis (2) | (2) | Energy/Utilities | July through January (2) |

| Socal Gas to Explore Feasibility of Providing Specialized Training and outsourcing Inspection Services for inclusion in PY2002 Recommendations (2) | (2) | SoCal Gas | July through May(2) |
| --- | --- | --- | --- |
| Utilities, with Energy Division, conduct workshops on presenting and standardizing training costs for inclusion in PY 2002 Applications (2) | (2) | Energy/Utilities | July through May (2) |
| Utilities, with Energy Division ,to develop consistency in competitive-bidding processes for PY2002 (2) | (2) | Energy/Utilities | July through May (2) |
| Utilities to Develop Cost Information on Competitive Bidding (2) | (2) | Utilities | July through May (2) |
| Utilities to Develop Alternatives to per-home pass rates as an indicator of performance quality (2) | (2) | Utilities | July through May (2) |
| Solicitation of New LIAB members |  | LIAB | July - August |
| Develop LIAB Draft Budget for 2001 |  | LIAB | July – August |
| WIS Project Meeting: General P&P (incl. CO/CAS) (San Francisco) | (3) | WIS | July 6 |
| LIAB Meeting – San Francisco |  | LIAB | July 10 & 11 |
| WIS Project Meeting: Mobile Home Standards (San Francisco) | (3) | WIS | July19 |
| LIAB TC Meeting – Los Angeles |  | TC | July 25-26 |
| WIS Project Meeting: Presentation to LIAB | (3) | WIS | July 26 |
| WIS Project Meeting: Final Clean-up (Los Angeles) | (3) | WIS | July27 |
| Final Workplan on Needs Assessment Issued | E-3646 | Energy | July 30 |
| LIAB Meeting – San Francisco |  | LIAB | August 1 & 2 |
| WIS Project Meeting: Presentation to LIAB | (3) | WIS | August 1 |
| WIS Project Draft Phase 2 Report | (3) | WIS | August 7 |
| WIS Project Meeting (San Diego) | (3) | WIS | August 22 |
| ACR Adoption of LIAB Bylaws |  | CPUC | ? |
| LIAB TC Meeting – San Diego |  | TC | August 15-16 |
| LIAB Meeting – Los Angeles |  | LIAB | August 29 &30 |
| WIS Project Meeting: Presentation to LIAB | (3) | WIS | August 29 |
| RFP Issued for Needs Assessment | E-3646 | Energy | August 29 (1) |
| WIS Project Final Phase 2 Report | (3) | WIS | August 31 |
| WIS Phase 2 Report Due | (3) | WIS | September 1 |
| LIAB Budget Filing |  | LIAB | September 1 |
| Submit nominations for LIAB 2001 |  | LIAB | September 1 |
| Utility PY 2001 Compliance Filings | (5)(3) | Utilities | September 1 |
| LIAB TC Meeting – San Francisco |  | TC | September 12-13 |
| LIAB Meeting – Monterey |  | LIAB | September 19 & 20 |
| LIAB and Party Comments on WIS Phase 2 | (3) | LIAB | ? |
| Utility Report on Licensing Status (2) | (2) | Utilities | 120 days from Signed Decision (2) |
| Workshops on Pay for Measured Pilot Design (2) | (2) |  | October Through January (2) |
| Report on RRM and Admin Costs Submitted | (4) | WG | October 1 |
| Comments on LIAB Budget Submittal | (3) | Parties | October 1 |
| Utility Report on CBO Participation (2) | (2) | Utilities | October 1 (2) |
| LIAB TC Meeting – Sacramento |  | TC | October3-4 |
| LIAB Meeting – Fresno |  | LIAB | October 17 & 18 |
| Reply Comments on WIS Phase 2 |  | Utilities | ????? |
| LIAB & Party Comments on RRM Report | (4) | LIAB & Parties | October 21 |
| Needs Assessment Proposals Analyzed, Bidder Selected | E-3646 | Energy | October 28 |
| Comments on CBO Report (2) | (2) | Parties | October 31 (2) |
| LIAB TC Meeting – Los Angeles |  | TC | November 1-2 |
| Reply Comments on RRM | (4) | Utilities | November 5 |
| Needs Assessment Contractor Begins Work | E-3646 | Energy | November 7 (1) |
| Reply Comments on CBO Report (2) | (2) | Utilities | November 15 (2) |
| LIAB Meeting – San Francisco |  | LIAB | November 14 & 15 |
| LIAB TC Meeting – San Francisco |  | TC | November 28-29 |
| Commission Adoption of RRM & Nonconsensus Items |  | CPUC | ? |
| LIAB Meeting – San Francisco |  | LIAB | December 12 & 13 |
| New WIS Manual Submitted As Compliance Filing |  | WIS | December 15 |
| LIAB TC Meeting – San Diego |  | TC | December 19-20 |
| Needs Assessment: Contractor Submits Draft Phase 1 Report on Study Design & RFP for Phase 2 | E-3646 | Energy | January 6 (1) |
| Needs Assessment: Public comments on Draft Phase 1 Report and Study | E-3646 | Parties | January 26 (1) |
| Applications on Pay For Measured Savings Pilot (2) | (2) | Utilities | February 1 (2) |
| Utility Report on Proposal to Standardize Data on Bill Savings and Expenditures for LIEE on Overall and Per Unit Basis (2) | (2) | Utilities | February 1 (2) |
| Needs Assessment: Energy Division Issues Final Report and RFP for Public Comment Period | E-3646 | Energy | February 25 (1) |
| Comments on Utility Proposal Submitted on February 1 on Standardizing Reporting of Bill Savings and Per Unit Costs (2) | (2) | Parties | March 3 (2) |
| Update on Utility Report on CBO Participation (2) | (2) | Utilities | April 1 (2) |
| ACR? authorizing Phase 2 Study Plan and RFP of Needs Assessment |  | CPUC | April 27 (1) |
| Comments on CBO Report (2) | (2) | Parties | May 1 (2) |
| Utility Annual Reports |  | Utilities | May 1 |
| Energy Division Letter on CARE Income Guidelines |  | Energy | May 1 |
| Needs Assessment Phase 2 RFP Issued | E-3646 | Energy | May 2 (1) |
| Reply Comments on CBO Reports (2) | (2) | Utilities | May 16 (2) |
| Utility Advice Letters on CARE Income Guidelines |  | Utilities | May |
| Needs Assessment Phase 2 Proposals Reviewed and Contractor Selected | E-3646 | Energy | June11 (1) |
| Needs Assessment: Independent Contractor Begins Phase 2 | E-3646 | Energy | July 11 (1) |
| Utility Submittal on PY2002 |  | Utilities | ??? |

Notes:

- Dates for Needs Assessment may slip based on Department of General Services Approval Process for RFP.

- Required by PD in A.99-07-002, et al. Decision not signed

- May 24, 2000 ALJ Ruling

- April 28, 2000 ACR

- March 26, 1999 ACR

- This schedule does not yet reflect dates from the recent AEAP Decision