# Schedule for Activities Leading to Revised Needs Assessment Report

| Milestone / Activity | Target Completion Date |
| --- | --- |
| Submit data request to utilities | 3/9 |
| Eligibility estimation meeting with utilities | TBD (Targeting 3/28) |
| Meet with CPUC to discuss/finalize sections of the final report that will be revised. | 3/30 |
| Obtain CARE and LIEE participation data request from utilities | 4/6 |
| Present revised final report to CPUC for internal review | 4/16 |
| Obtain CPUC comment on revised final report | 4/30 |
| Present final report for CPUC internal approval | 5/14 |
| Present final report to public | 5/28 |
| PUC to adopt final KEMA report | Summer 2007 |