| Accomplishments to Date for LIEE and CARE | Date |
| --- | --- |
| Utilities and KEMA meet to review data concerns (Needs Assessment Study) | January – February |
| PG&E, SCE, Sempra, and Energy Division staff work with CHHS to enroll eligible customers in CARE pursuant to SB 580 (D.06-12-038; OP 11) | January – March |
| PG&E, SCE, and Sempra file program proposals for water conservation efforts in R.06-04-010 (EE proceeding) | January 15 |
| LIOB Meeting | January 17 |
| Pre-Hearing Conference on Water Conservation (R.06-04-010) | January 30 |
| Commission issues Low Income Order Instituting Rulemaking (OIR) (R.07-01-042) | January 31 |
| SCE submits modified marketing plan to Energy Division (D.06-12-038; CL 13 and OP 12) | February 15 |
| SCE presents program proposal to Energy Division re: Catalina Island Pilot (D.06-12-038; CL 11) | February 15 |
| PG&E submits advice letter to Energy Division with plan and proposed budget for establishing and opening cool centers by summer of 2007 ( D.06-12-038; CL 20 and OP 13) | February 15 |
| SDG&E and SCG jointly petition to modify D.06-12-038 SCE petitions to modify D.06-12-038 PG&E and SDG&E jointly petition to modify D.06-12-038 | February 20 March 30 April 10 |
| Workshop to streamline monthly and annual reporting (D.06-12-038; OP 9) | February 21 |
| Initial OIR comments filed (R.07-01-042) | February 25 |
| Utilities meet with Energy Division to discuss process for competitive bidding process for future LIEE administrator (D.06-12-038; OP 6 and 14) | March |
| Pre-Hearing Conference: LIEE OIR (R.07-01-042) | March 7 |
| Energy Division and CPUC Audit Department meet to discuss audit plan for IOUs. | March 9 |
| LIOB meeting | March 22 |
| Workshop on objectives and goals of the LIEE program (R. 07-01-042) | March 23 |
| Assigned Commissioner issues scoping ruling to guide parties regarding procedures and management of LIEE OIR | March 28 |
| Workshop on AB 2104 (R. 07-01-042) | April 17 |
| Comments on joint petition of PG&E and SDG&E to modify D.06-12-038 | April 18 |
| Reply comments on joint petition of PG&E and SDG&E to modify D.06-12-038 | April 20 |
| Reply comments on workshop regarding objectives and goals of the LIEE program (R. 07-01-042) | April 27 |
| Commission approves PG&E’s cool center proposal | May 3 |
| Reply comments on workshop regarding objectives and goals of the LIEE program (R. 07-01-042) | May 8 |
| Workshop on renters’ issues (R. 07-01-042) SCE submits advice letter on compact fluorescent light program | May 10 |
| Administrative Law Judge issues ruling soliciting comments on renters and AB 2104 issues | May 22 |
| Draft of Final KEMA Needs Assessment Report (KEMA Study) | end of June |
| Comments on renter access and AB 2104 (R. 07-01-042) | June 2 |
| Assigned Commissioner issues ruling inviting applications to the Low-Income Oversight Board | June 4 |
| Energy Division approves SCE’s Catalina Island Pilot | June 6 |
| Commission considers Low-Income Oversight Board Charter Commission considers proposed decision to grant petitions to modify D. 06-12-038 | June 7 |
| Workshop on natural gas appliance testing issues (R. 07-01-042) | June 13 |
| Reply comments on renter access and AB 2104 (R. 07-01-042) | June 15 |
| Impact Evaluation Meeting | February 5 April 16 June 7 |
| Quarterly public meetings for parties to share ideas to influence improvements to program elements, processes, and practices (D.06-12-038; CL 9 and OP 7) | March 13 and 27 June 11 and 12 (Ongoing – no less than every 90 days) |

| Upcoming Activities for LIEE and CARE | Date 1, |
| --- | --- |
| Energy Division and CPUC Audit Department meet to discuss audit plan for IOUs. | June 22 |
| Draft Impact Evaluation Report | mid-July |
| Finalize streamlining monthly and annual reporting (D.06-12-038; OP 9) | July 16 |
| Comment period for Draft Impact Evaluation Report | mid-July to August |
| LIOB Meeting Presentation of Final Impact Evaluation Study Report | September |
| Submit Impact Evaluation Study Report to Commission | October 31 |
| Commission issues LIEE OIR Phase I decision | Fall |
| Commission approves LIEE OIR Phase I decision | Winter |
| Commission completes financial audits of utilities’ LIEE accounts and programs (D.06-12-038; OP 11) | February 1, 2008 |

# Footnotes

All dates are in the year 2007 unless otherwise noted.

All Dates in this list should be considered tentative.