# BEFORE THE PUBLIC UTILITIES COMMISSION

OF THE STATE OF CALIFORNIA

| Order Instituting Rulemaking on the Commission’s Proposed Policies and Programs Governing Post-2003 Low Income Assistance Programs. | ##### Rulemaking 04-01-006 |
| --- | --- |

REPORT OF SOUTHERN CALIFORNIA GAS COMPANY

(U 904 G) ON RAPID DEPLOYMENT EFFORTS FOR YEAR-END 2003

GEORGETTA J. BAKER

Attorney for

Southern California Gas Company

101 Ash Street, HQ13D

San Diego, CA  92101-3017

Telephone:  (619) 699-5064

Facsimile:  (619) 699-5027

E-Mail: gbaker@sempra.com

# February 23, 2004

BEFORE THE PUBLIC UTILITIES COMMISSION

OF THE STATE OF CALIFORNIA

| Order Instituting Rulemaking on the Commission’s Proposed Policies and Programs Governing Post-2003 Low Income Assistance Programs. | ##### Rulemaking 04-01-006 |
| --- | --- |

REPORT OF SOUTHERN CALIFORNIA GAS COMPANY

(U 904 G) ON RAPID DEPLOYMENT EFFORTS FOR YEAR-END 2003

I.	INTRODUCTION

In Decision (D.) 01-05-033 the Commission directed the Southern California Gas Company (SoCalGas) and the other utilities to provide monthly status reports on the costs and impacts of their Rapid Deployment (RD) efforts associated with the California Alternate Rates for Energy (CARE) and Low Income Energy Efficiency (LIEE) programs.  On May 22, 2002, the utilities held a conference call with the Energy Division and the Office of Ratepayer Advocates to assess RD Reporting.  The parties agreed that the utilities would submit a full monthly RD report to the Commission beginning in the May 2002 report, and with future full reports due in August 2002, November 2002 and February 2003, and continuing at three-month intervals.  The utilities and Energy Division later agreed that the final year-end report for PY2003 would be submitted on February 23, 2004.  Pursuant to this agreement, this full year-end closing report includes all quantitative tables for the program year 2003 as well as detailed information on SoCalGas’ outreach efforts and media advertising.

In D.02-07-033, the Commission authorized the IOUs to update their CARE and LIEE forecasts per the Reporting Requirements Manual (RRM) each June.  Pursuant to this Decision and a subsequent Assigned Commissioner Ruling dated 12/27/02, SoCalGas completed an update of its CARE and LIEE eligibility estimates and has used this updated information to provide information on CARE and LIEE customer participation and penetration for PY2003.  An explanation of this update was filed with SoCalGas’ February 21, 2003 RD Report.

# Low-Income Energy Efficiency (LIEE)

Year-End 2003 Results—Installations

SoCalGas processed and paid for the installation of weatherization measures in 47,673 homes during the year.

The appliance program serviced a total of 9,506 appliances for 2003, which represents 546 furnace repairs, 4,252 furnace replacements and 4,708 water heater replacements.

During the year, SoCalGas processed and expensed reimbursements for 917 Energy Education Workshops with a total of 20,035 participants.

LIEE measure and appliance installations processed and paid during the month of December 2003, and year-to-date, can be found in SoCalGas’ Table 4, LIEE Measure Installations.  All installations for PY2003 are from base funds as all SBX15 allocations were expensed in PY2002.

Table 5 provides the LIEE estimated therm savings for the month of December 2003 and year-to-date.  Summary Tables 25 through 27 provide additional breakdown of customer energy and bill savings for the LIEE program activities.  Table 5A also presents estimated bill savings for the month of December 2003 and year-to-date, with related Summary Tables 25 through 27, which provide additional breakdown related to customer energy and bill savings for the LIEE program activities.

## Leveraging and Outreach

Table A of this report provides an outline of LIEE Outreach and Leveraging activities for Program Year 2003.

During PY2003, SoCalGas leveraged LIEE outreach with other Customer Assistance outreach efforts at numerous community events.  Many of these events were in partnership with local governments, charity organizations, schools and businesses.  Some of the events attended included the PAN Asian American Expo, the PAN African American Film Festival, the Riverside Black History Parade and Expo, Operation Hope, the City of Maywood Cinco De Mayo event, the Reginald Gentry Career Day, Head Start All-Staff meeting, the LA County School District, The New Leaders Health and Wellness Fair, the Buena Park Senior Center, the Anaheim Senior Center, the Garden Grove Senior Center, La Mirada High School, the Asian Pacific Community Fund, the Joint Forces Training Base (JFTB), the Santa Ana Neighborhood Network, the Riverside Expo, the Black Business Expo, the LA County Fair, the Harvest Moon Festival, the Westminster Energy Fair, the Church of Nativity October fest, the Magic Johnson Adventure Center, and the Hollenbeck Middle School.  During these events customers were given brochures in different languages as well as applications for the programs.  SoCalGas representatives were also available to answer any questions customers might have regarding the various programs and services available.

SoCalGas also continued distribution of Customer Assistance Program (CAP) brochures to all company bases.  For 2003, Energy Technicians distributed over 76,000 CAP brochures to interested customers.

LIEE Authorized Funding Versus Actual Expenditures

SoCalGas’ Table 1, LIEE Program Expenses, reflects detailed budget allocations and program expenditures for the month of December and year-to-date 2003.  The LIEE program expenditures totaled approximately $30.2 million for services processed and paid during the year.  An additional $3.8 million was spent on administration.  Total costs year-to-date are 89% of budget.

- CALIFORNIA ALTERNATE RATES FOR ENERGY (CARE)

PY2003 CARE Enrollment Results

SoCalGas had 957,602 customers enrolled in the CARE program at year-end 2003, a net gain of 167,010 customers (see Table 10) for a penetration rate of 69 percent.  New CARE enrollments for the year totaled 467,223 customers.  RD contractors’ submitted 73,471 applications that resulted in 54,595 (74 percent approved) new CARE enrollments.

PY2003 Outreach and Leveraging

Table B and Table C of this report provides an outline of CARE Outreach and Leveraging and Media activities for Program Year 2003.

Forty-three (43) RD agencies continued to provide applications for processing and approval of the hard-to-reach customers.  In addition to outreach through the capitation agencies, SoCalGas continues to communicate CARE information to its customers through bill inserts, newsletters and community events.  Outreach efforts are conducted in English, Spanish, Korean, Chinese and Vietnamese.  SoCalGas continues to receive and respond to requests for CARE applications and/or CAP brochures due to the increased awareness of the low-income programs in the SoCalGas service territory.

CARE Authorized Funding Versus Actual Expenditures

PY2003 CARE administrative expenses for base and rapid deployment programs totaled $4.4 million, which is 81 percent of the authorized 2003 CARE budget.  CARE discounts and service establishment charges for the year are $53 million, which is 115 percent of the authorized 2003 CARE budget.  SoCalGas’ remaining balance of approximately $747 thousand under its rapid deployment contract with the Commission for CARE program outreach and administrative was completely expended in September 2003.  Actual expenses are compared to budgeted figures in Table 6 for both the base program and the SBX1 5 RD program.

IV.	CONCLUSION

SoCalGas implemented its RD efforts with the goal of providing LIEE services to as many qualified customers as possible and increasing CARE participation during PY2003.  As a result, SoCalGas added 167,010 customers to its CARE program participation and 47,673 customers received weatherization services.

Respectfully submitted,

By: ___________________________________

Georgetta J. Baker

Attorney for

Southern California Gas Company

101 Ash Street, HQ13D

San Diego, CA  92101-3017

Telephone:  (619) 699-5064

Facsimile:  (619) 699-5027

E-Mail: gbaker@sempra.com

# February 23, 2004

#### Certificate of Service

I hereby certify that I have this day served a copy of the foregoing Report of Southern California Gas Company (U 904 G) on Rapid Deployment Efforts for Year End 2003 on all parties identified in R.01-08-027 on the attached service list by U. S. mail and electronic mail, and by Federal Express to Commissioner Carl W. Wood and Administrative Law Judge Sarah Thomas.

Dated at San Diego, California, this 23rd day of February 2004.

# Laurie Delaney