# Proposal Requirements

## Time Schedule for Submission and Review of Proposals

It is recognized that time is of the essence.  All proposers are hereby advised of the following schedule and will be expected to adhere to the required dates and times.  The following table shows the timetable of events:

Table ‎4-1:  Timetable of Events					      Tentative Dates

| Event | Date |
| --- | --- |
| Request for Proposal issued and advertised | May 15, 2002 |
| Deadline for written questions regarding this Request for Proposal | June 7, 2002 |
| Proposals are submitted no later than 2:00 p.m. | June 17, 2002 |
| Evaluation of written bids complete | July 1, 2002 |
| Bidder interviews start | July 8, 2002 |
| Bidder interviews end | July 12, 2002 |
| Evaluation of proposals completed | July 19, 2002 |
| Public bid opening held at 505 Van Ness Ave. | July 22, 2002 |
| Proposed award notice will be posted at 505 Van Ness Avenue | July 23, 2002 |
| Contract awarded (if no protest is filed by deadline) | July 29, 2002 |
| Contract approved and signed by the Commission & consultant (date approximate) | August 2, 2002 |
| Department of General Services approves contract (date approximate) | August 23, 2002 |
| Contract work starts (date approximate, contract and funding have to be approved by the Department of General Services and the Commission before work may begin) | September 1, 2002 |

## Work Plan and Schedule Requirements

### Phase II Tasks

The following lists the deliverables and estimated target completion dates for Phase II tasks.  Note that all dates are tentative.

(	Task 1: Refine the Work Scope.  Finalize the study goals and objectives, specific tasks, and the schedule and budget, and produce a detailed final research plan.

(	Deliverable:  Final Research Plan

(	Target completion date:  September 15, 2002

(	Task 2: Provide Opportunity for Public Input (ongoing throughout project).  Conduct public workshops at key intervals to allow review of project milestones and deliverables.

(	Deliverable:  Summary of comments following each workshop

(	Target completion date: August 31, 2003

(	Task 3: Conduct the Onsite Surveys.  Conduct the sample design, design the survey instruments and implementation plan, and collect and analyze survey response data.

(	Deliverables: Completed sample design, survey instruments, disposition report, tabulated results

(	Target completion date: March 15, 2003

(	Task 4: Analyze Census Data.  Obtain 2000 Census data and update with commercial vendor distributions of household income and household size.

(	Target completion date: April 15, 2003

(	Task 5: Develop Estimates of Potential.  Create estimates of potential as outlined in the Phase I Final Report for the CARE and LIEE programs.

(	Deliverable: Estimates for indicators of CARE and LIEE potential by county, utility area and fuel type

(	Target completion date: June 15, 2003

(	Task 6: Characterize the Eligible Population.  Develop a characterization of the customers who are eligible for CARE and LIEE, including demographic, housing and geographic characteristics.

(	Deliverable: Draft report with final incorporated into Phase II Report

(	Target completion date: June 30, 2003

(	Task 7: Assess the Needs of the Eligible Population.  Provide a detailed report on customer needs, concerns, and perceptions as identified in the Phase I Final Report.
(	Deliverable: Draft report with final incorporated into Phase II Report

(	Target completion date: July 31, 2003

(	Task 8: Recommendations for Results.  Provide recommendations on how Phase II results should be addressed.

(	Deliverable: Draft report with final incorporated into Phase II Report

(	Target completion date: July 31, 2003

(	Task 9: Develop a Method to Track Penetration Over Time.  Using the base year results from Phase II, develop a methodology for updating, collecting, and reporting information on CARE and LIEE penetration and remaining potential.

(	Deliverable: Draft report with final incorporated into Phase II Report

(	Target completion date: July 31, 2003

(	Task 10: Develop a Phase II report.

(	Deliverable: Draft and final reports

(	Target completion date: August 31, 2003

(	Task 11: Provide Technical Support.  Provide technical support to the Energy Division staff as requested, and make any additional revisions ordered by the Commission.

(	Target completion date: August 31, 2003

## Cost Detail Format

The proposed work should be broken down into the Work Plan and Work Schedule for the purpose of this proposal.  The total costs of all tasks and milestones cannot exceed $888,000.  Use the Sample Cost Proposal Worksheet (Attachment 3 in Section 5 of this RFP) as a guide in preparing your cost proposal.

## Format of Proposals

The proposal shall include the following information:

### Overview of Proposal

Describe the purpose and objectives of the study and how the proposal is arranged.

### Bidders Business Information

- State your firm’s full name, address, and, if applicable, the branch office and any subcontractors that would perform or assist in performing any of the work.

- Designate persons authorized to act on behalf of your firm during contract negotiations.

- State your earliest available starting date.

- State the names, addresses, and telephone numbers of the key personnel of your firm who would be working as consultants.  Include a copy of each key staff member’s resume.

- Include a management and organization chart of the proposed organization and team, including any Prime Contractor and subcontractor relationships.

- Show the proposed relationships between the project Coordinator, key personnel, support staff and other resources that are expected to participate in the project, showing which aspects of the work each person will be responsible for performing and the approximate percentage of his/her time devoted to the project.

- If subcontractors are a part of the bidder’s team, the requested information, including current resumes, must be provided for them as well as the Prime Contractor.

- The proposal should designate the key personnel assigned to this contract with the understanding that Energy Division will require that all professional work billed under this contract be performed by the identified personnel, with approximately the same time commitment as indicated in the organization chart.

### Technical Issues

Discuss the technical issues involved in conducting this needs assessment, including those presented in this RFP and in the Phase I Final Report.

### Work Tasks

Submit a detailed work plan for accomplishing the tasks outlined in this RFP.  A detailed work plan should include the following:

(	Describe the management process by which the deliverables specified in the Scope of Work will be accomplished.

(	Describe your firm’s management procedures for planning, scheduling, and budgeting, as well as the procedures to be used in controlling time used, dollars spent, and quality control over deliverables.

(	Describe the specific steps your firm intends to complete in performing the project tasks.

(	Describe prospective arrangements to remain in contact and to coordinate with the Commission’s Contract Manager and consultant team.

### Project Schedule

Submit a schedule for accomplishing the analysis and delivering work products.  The proposer should provide a conservative project timeline that estimates the number of days to complete each task element identified in the workplan, identifies and accounts for all possible delays, and meets the target deadlines with a high degree of certainty.

### Staffing Plan

The proposal should include the personnel assigned to each task and the number of hours for each staffing type or staff level needed to complete each deliverable.

### Qualifications

The proposal should also include the following supporting documentation:

(	Describe all applicable qualifications and provide detailed explanation of special capabilities directly related to conducting demographic studies.

(	Fully describe all previous experience designing demographic or needs assessment studies, and provide examples of previous deliverables.

(	Describe all applicable qualifications and provide detailed explanation of special capabilities directly related to conducting surveys of housing stock and weatherization measures.

(	Fully describe all previous contract work done with any of the investor owned or municipal utilities in California in the past five years.

(	Provide Energy Division staff with examples of previous work products.  Provide a list of similar previous studies/reports and list of sponsor references.

### Forms and Attachments

Attachments to be submitted with the proposal are provided in Section 5.

## Submission Procedures

### Submission Requirements

Proposers must comply with the following submission requirements:

1.	Proposals should provide straightforward and concise descriptions of the proposer's ability to satisfy the requirements of this RFP.  The proposal must be complete and accurate.  Omissions, inaccuracies, or misstatements will be sufficient cause for rejection of a proposal.

2.	Due to limited storage space, the proposal package should be prepared in the least expensive method (i.e., cover page with staple in upper left-hand corner, no fancy bindings).

3.	All proposals must be submitted under sealed cover and received at the CPUC by June 17, 2002 by 2pm.  Proposals received after this date and time will not be considered.

4.	A minimum of four (4) copies of the proposal must be submitted.

5.	The original proposal must be marked "ORIGINAL COPY."  All documents contained in the original proposal package must have original signatures and must be signed by a person who is authorized to bind the proposing firm.  All additional proposal sets may contain photocopies of the original package.

6.  The proposal package must be plainly marked with the RFP number and title and your firm name and address, and must be marked with "DO NOT OPEN", as shown in the following example:

RFP (01PS-5235)
Low-Income Needs Assessment Study, Phase II
Firm XYZ
Pawtucket, California 92111

DO NOT OPEN

If the proposal is made under a fictitious name or business title, the actual legal name of proposer must be provided.  

The bid price and all cost information must be submitted in a separate sealed envelope.  The envelope should be affixed to the outside of the proposal package and marked “Sealed Cost Proposal-DO NOT OPEN.”  Proposals not submitted under sealed cover and marked as indicated may be rejected.

7.	All proposals shall include the documents identified in Section 5, Attachment 1, Attachment Checklist .  Documents in your proposal must appear in the order that they are listed in Section 5, Attachment 1.

8.	Proposals must be mailed or delivered to the following address:

California Public Utilities Commission

Contracts Office, Second Floor

505 Van Ness Ave

San Francisco, CA 94102

9.	Proposals must be submitted for the performance of all the services described herein.  Any deviation from the work specifications will not be considered and will cause a proposal to be rejected.

10.	A proposal may be rejected if it is conditional or incomplete, or if it contains any alterations of form or other irregularities of any kind.  The State may reject any or all proposals and may waive any immaterial deviation in a proposal.  The State's waiver of immaterial defect shall in no way modify the RFP document or excuse the proposer from full compliance with all requirements if awarded the agreement.

11.	Costs for developing proposals are entirely the responsibility of the proposer and shall not be charged to the State of California.

12.	An individual who is authorized to bind the proposing firm contractually shall sign the Attachment 2 Proposal/Proposer Certification Sheet (Section 5).  The signature must indicate the title or position that the individual holds in the firm.  An unsigned proposal may be rejected.

13.	A proposer may modify a proposal after its submission by withdrawing its original proposal and resubmitting a new proposal prior to the proposal submission deadline.  Proposal modifications offered in any other manner, oral or written, will not be considered.

14.	A proposer may withdraw its proposal by submitting a written withdrawal request to the State, signed by the proposer or an agent authorized in accordance with number 8 above.  A proposer may thereafter submit a new proposal prior to the proposal submission deadline.  Proposals may not be withdrawn without cause subsequent to proposal submission deadline.

15.	The awarding agency may modify the RFP prior to the date fixed for submission of proposals by the issuance of an addendum to all parties who received a proposal package.

16.	The awarding agency reserves the right to reject all proposals for reasonable cause.  If all proposals exceed the authorized budget, the agency is not required to award a contract.

17.	Proposers are cautioned to not rely on the State during the evaluation to discover and report to the proposer any defects and errors in the submitted documents.  Proposers, before submitting their documents, should carefully proof them for errors and adherence to the RFP requirements.

18.	More than one proposal from an individual, firm, partnership, corporation or association under the same or different names, will not be considered.  Reasonable grounds for believing that any proposer has submitted more than one proposal for the work contemplated herein will cause the rejection of all proposals submitted by that proposer.  If there is reason to believe that collusion exists among proposers, none of the participants in such collusion will be considered in this or future procurements.

## Evaluation Procedures

### Proposal Evaluation Process

The following process will be used to evaluate Phase II proposals:

a)	At the time of proposal opening, each proposal will be checked for the presence or absence of required information in conformance with the submission requirements of this RFP.

b)	The State will put each proposal through a process of evaluation to determine its responsiveness to the State's needs.

c)	Proposals that contain false or misleading statements, or which provide references, which do not support an attribute or condition claimed by the proposer, may be rejected.  If, in the opinion of the State, such information was intended to mislead the State in its evaluation of the proposal, and the attribute, condition, or capability is a requirement of this RFP, it will be the basis for rejection of the proposal.

d)	Final selection will be based on the most responsive proposal with the lowest cost.

### Proposal Evaluation Steps

#### Step One

The proposals that meet the minimum qualifications will be evaluated and scored according to the criteria indicated below.  A minimum of 80 points must be achieved in this phase to be considered responsive.  (A responsive proposal is one which meets or exceeds the requirements stated in this RFP.)  These criteria were established by the Commission based on information presented above under Section 4.5.1 Submission Requirements.  Below is an example of possible rating categories:

(	25% quality of the team: relevant experience and capabilities.

(	25% responsiveness to the RFP: conceptual approach to accomplishing one or more tasks.

(	10% timeliness:  past record in providing deliverables and services on time and under budget.

(	20% quality of prior technical reports, financial records and preparation of meeting and administrative documents.

(	20% analytical techniques to be employed.

The maximum possible score in step 1 will be 100.  All bidders who score at or above 80% of the total points in step 1 will become finalists and will move on to step 2.

#### Step Two

Step two will consist of interviews and presentations from bidders who have achieved a score of 80 or higher in Step I.  Proposers will be evaluated on the quality of their presentations and their answers to standard interview questions.  The presentations should consist of the proposers proposals to achieve the work tasks identified in this RFP.  Presentations will be scored on the basis of a total of 100 possible points, with points distributed as follows:

(	40% Presentation

(	60% Answers to Interview Questions

All bidders who score at or above 85% of the total points in step 2 will become finalists and will move on to step 3.

#### StepThree

This step consists of opening and evaluating the sealed cost proposals.  All proposals that enter step 3 will have received 85 points or more in step 2 and are considered fully capable of performing the required services.  The sealed envelopes containing the bid price and cost information for the proposals that meet the format requirements and standards shall then be publicly opened and read.  The agreement will be awarded to the lowest responsible bidder meeting the requirements outlined in this RFP.  If no proposals are received containing bids offering a price, which in the opinion of the awarding agency is a reasonable price, the awarding agency is not required to award an agreement (Public Contract Code 10344 (d), 10377 (d)).

## Award and Protest

Contract awards and protests will be governed by the following terms:

a)	Whenever an agreement is awarded under a procedure that provides for competitive bidding, but the agreement is not to be awarded to the finalist who is also the low bidder, the low bidder shall be notified by telegram, electronic facsimile transmission, overnight courier, or personal delivery five (5) working days prior to the award of the agreement.

b)	Upon written request by any proposer, notice of the proposed award shall be posted in a public place in the office of the awarding agency at least five (5) working days prior to awarding the agreement.

c)	If any proposer, prior to the award of agreement, files a protest with the awarding agency on the grounds that the (protesting) proposer is the lowest responsible proposer, the agreement shall not be awarded until either the protest has been withdrawn or the Department of General Services has decided the matter.

d)	Within five (5) days after filing the initial protest, the protesting proposer shall file with the Department of General Services and the awarding agency a full and complete written statement specifying the grounds for the protest.  The written protest must be sent to the Department of General Services, Office of Legal Services, 1325 J Street, Suite 1911, Sacramento, California 95814.  A copy of the written protest must be mailed to the CPUC at the address in Section 4.5.1, paragraph 8.  It is suggested that you submit any protest by certified or registered mail.

e)	Upon award of the agreement, Contractor must complete and submit to the awarding agency the Payee Data Record (STD 204), to determine if the Contractor is subject to state income tax withholding pursuant to California Revenue and Taxation Code Sections 18662 and 26131.  This form can be found on the Internet at www.osp.dgs.ca.gov under the heading FORMS MANAGEMENT CENTER.  No payment shall be made unless a completed STD 204 has been returned to the awarding agency.

f)	Upon award of the agreement, Contractor must sign and submit to the awarding agency, page one (1) of the Contractor Certification Clauses (CCC), which can be found on the Internet at www.dgs.ca.gov/contracts.  This document is only required if the proposer has not submitted this form to the awarding agency within the last three (3) years.

## Disposition of Proposals

Upon proposal opening, all documents submitted in response to this RFP will become the property of the State of California, and will be regarded as public records under the California Public Records Act (Government Code Section 6250 et seq.) and subject to review by the public.  The State cannot prevent the disclosure of public documents.  However, the contents of all proposals, draft proposals, correspondence, agenda, memoranda, working papers, or any other medium which discloses any aspect of a proposer's proposal, shall be held in the strictest confidence until the “Letter of Intent” (contract award) is posted.

Proposal packages may be returned only at the proposer's expense, unless such expense is waived by the awarding agency.

## Standard Conditions of Service

The following standard conditions of service will be enforced:

a)	Service shall be available not later than September 1, 2002, after all approvals have been obtained and the agreement is fully executed.  Should the Contractor fail to commence work at the agreed upon time, the awarding agency, upon five (5) days written notice to the Contractor, reserves the right to terminate the agreement.  In addition, the Contractor shall be liable to the State for the difference between Contractor's Proposal price and the actual cost of performing work by the second lowest proposer or by another contractor.

b)	All performance under the agreement shall be completed on or before the termination date of the agreement.

c)	The State does not accept alternate contract language from a prospective contractor.  A proposal with such language will be considered a counter proposal and will be rejected.  The State’s General Terms and Conditions (GTC) are not negotiable.  The GTC may be viewed at Internet site www.dgs.ca.gov/contracts.

d)	No oral understanding or agreement shall be binding on either party.

## Preference Programs

The standard contract language for the preference programs can be found at the Internet web sites listed below:

1.	Small Business Enterprise (SBE)

www.osmb.dgs.ca.gov/program.htm

2.	Target Area Contract Preference Act (TACPA)

www.osmb.dgs.ca.gov/tacpa/program.htm

3.	Local Agency Military Base Recovery Area (LAMBRA) Act

www.osmb.dgs.ca.gov/lambra/program.htm

4.	Enterprise Zone Act (EZA)

www.osmb.dgs.ca.gov/eza/program.htm

5)	Standard contract language for the Disabled Veteran Enterprise Program (DVBE)

www.osmb.dgs.ca.gov/dvbepp/program.htm

To view the DVBE package and obtain the required submittal forms, go to the web site listed above.

## Required Attachments

A complete proposal or proposal package will consist of the items identified below.  For your proposal to be responsive, all required attachments must be returned.  If an attachment is not applicable to your firm, you must indicate “Not Applicable” on the form, sign it, and return it with your proposal.  Attachments 1 through 6 are applicable to all bidders.

(	Attachment 1:	Attachment Check List

(	Attachment 2:	Proposal/Proposer Certification Sheet

(	Attachment 3:	Cost Sheet (submitted under separate cover)

(	Attachment 4:	Disabled Veteran Business Enterprise Participation Forms and Instructions

(	Std. 840 Disabled Veteran Business Enterprise Participation Summary (page 1)

(	Good Faith Effort Documentation – Exhibit A

(	Attachment 5:	Payee Data Record (STD 204) (if currently not on file) (may be found at www.osp.dgs.ca.gov)

(	Attachment 6:	Contractor Certification Clauses (CCC201).  (The CCC can be found at www.dgs.ca.gov/contracts.  Page one (1) must be signed and submitted prior to the award of the agreement, but is not required if the proposer has submitted this form to the awarding agency within the last three (3) years.)

(	Attachment 7:	Target Area Contract Preference Act (TACPA)

(	Attachment 8:	Enterprise Zone Act (EZA)

(	Attachment 9:	Local Agency Military Base Recovery Area (LAMBRA ) Act

Section 5 contains copies of Required Attachments 1 through 3 that are a part of this agreement.  Attachments 4 through 9 must be downloaded from the Department of General Services web site.