| Week of | LIGB Meetings | Board Structure Oper Procedure/ Needs Assessment | Program Plan & Comp.-Bidding PY2000/2001 | Program Review PY99 & Future | Standardized Rptg & Standardized Admin Costs | Pilots | AEAP: 2000 & 2001 Issues | Other |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Aug 30 |  |  | Draft Request for Joint Utility Proposal on Standardization for 2001 Summarize Reply Comments Prepare Critical Path Table Comp-Bid ALJ Scoping memo – Mailed Sept 3 |  | On Hold - ALJ Unassigned |  | AEAP Hearings | Review Invoices and Expenses Web Updates SMUJ Table Fin Tracking Nominees Filing Sept 1 |
| Sept 6 | Sept 8 & 9 San Fran | Prop Decision on Workshop Rept – Mailed Sept 7 |  |  |  |  | AEAP Hearings | Review Invoices and Expenses Web Site Updates Draft Minutes Define Support Tasks for Sept - Oct |

| Week of | LIGB Meetings | Board Structure Oper Procedure/ Needs Assesment | Program Plan & Comp.-Bidding PY2000/2001 | Program Review PY99 & Future | Standardized Rptg & Standardized Admin Costs | Pilots | AEAP: 2000 & 2001 Issues | Other |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sept 13 |  |  | Comp-Bid RFP and Testimony Due (Sept 17) |  |  |  | Opening Briefs (Sept 14) | Review Invoices and Expenses Web Site Updates |
| Sept 20 |  |  | Review Comp-Bid Testimony – Begin LIGB Report |  |  |  | Reply Briefs (Sept 21) | Review Invoices and Expenses Web Updates |
| Sept 27 | Sept 29 San Fran | File Comments on Proposed Decision Sept. 27 | Work in LIGB Report Submit Request for Joint Utility Proposal on Standardization for 2001 | 3 Advice Letters on CARE Applications AL 2183-G PGE AL1190-E SDGE AL 2845-G SCG |  |  |  | Review Invoices and Expenses Web Updates |
| Oct 4 |  | Final Decision on Workshop Rept? Oct 7? Draft Compliance Filing on Board Bylaws and Policy Rules? | Comp-Bid Intervenor Testimony Oct 8 Optional joint Motion for Bifurcation Oct 8 Review Intervenor Testimony – Add to LIGB Report |  |  |  |  | Review Invoices and Expenses Web Updates Fin Tracking |

| Week of | LIGB Meetings | Board Structure Oper Procedure/ Needs Assessment | Program Plan & Comp.-Bidding PY2000/2001 | Program Review PY99 & Future | Standardized Rptg & Standardized Admin Costs | Pilots | AEAP: 2000 & 2001 Issues | Other |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Oct 11 | Oct 12 &13 Fresno | Approve Compliance Filing on Board Bylaws and Policy Rules? | Approve LIGB Report File LIGB Report Oct 15 Reply comments on Any Draft Motion Oct 13 |  |  |  |  | Review Invoices and Expenses Web Site Updates Draft Minutes Define Support Tasks for Oct - Nov |
| Oct 18 |  |  | Comp-Bid Reply Testimony (Oct 20) |  |  |  |  |  |
| Oct 25 |  | Compliance Filing: Revised Charter & Bylaws Oct 27? Review Draft Needs Assess Reso? Prepare LIGB comments on Draft Needs Assess Resolution? | Comp-Bid Case Mgmnt -Joint Exhibit (Oct 27) |  |  |  |  | Review Invoices and Expenses Web Site Updates |
| Week of | LIGB Meetings | Board Structure Oper Procedure/ Needs Assessment | Program Plan & Comp.-Bidding PY2000/2001 | Program Review PY99 & Future | Standardized Rptg & Standardized Admin Costs | Pilots | AEAP: 2000 & 2001 Issues | Other |
| Nov 1 |  | Review Draft Nds Asses Reso? Prepare LIGB comments on Draft Nds Asses Resolution? | Comp-Bid Hearings Nov 1-5 |  |  |  | Proposed Decision Nov 2 | Review Invoices and Expenses Web Site Updates |
| Nov 8 | Nov 9 & 10 Stockton | Approve Board Comments on Draft Nds Asses Reso? |  |  |  |  |  | Review Invoices and Expenses Web Site Updates Draft Minutes Define Support Tasks for Nov - Dec |
| Nov 15 |  |  |  |  |  |  |  |  |
| Nov 22 |  |  | Comp-Bid Opening Briefs (Nov 24) |  |  |  |  |  |
| Nov 29 |  |  |  |  |  |  | Commission Decision Dec 2 |  |
| Dec 6 |  |  | Reply Briefs (Dec 9) |  |  |  |  |  |
| Week of | LIGB Meetings | Board Structure Oper Procedure/ Needs Assessment | Program Plan & Comp.-Bidding PY2000/2001 | Program Review PY99 & Future | Standardized Rptg & Standardized Admin Costs | Pilots | AEAP: 2000 & 2001 Issues | Other |
| Dec 13 | Dec 14 & 15 San Fran |  |  |  |  |  |  | Web Site Updates Draft Minutes Define Support Tasks for Dec - Jan |
| Dec20 |  |  |  |  |  |  |  |  |
| Dec 27 |  |  |  |  |  |  |  |  |