BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF CALIFORNIA

| In the Matter of the Application of Southern California Gas Company (U 904 G) for Approval of Program Year 2003 Low-Income Assistance Programs and Funding | Application 02-07-001 (Filed July 1, 2002) |
| --- | --- |
| Application of San Diego Gas & Electric Company (U 902 E) for Approval of Program Year 2003 Low-Income Assistance Programs and Funding. | Application 02-07-002 (Filed July 1, 2002) |
| Application Of Pacific Gas And Electric Company (U 39 M) For Approval Of The 2003 California Alternate Rates For Energy and Low-Income Energy Efficiency Programs and Budget. | Application 02-07-003 (Filed July 1, 2002) |
| Southern California Edison Company’s (U 338-E) Application Regarding Low-Income Assistance Programs for Program Year 2003. | Application 02-07-004 (Filed July 1, 2002) |
| Order Instituting Rulemaking on the Commission’s Proposed Policies and Programs Governing Low-Income Assistance Programs. | Rulemaking 01-08-027 (Filed August 23, 2001) |

ASSIGNED COMMISSIONER’S RULING REVISING THE SCHEDULE FOR PHASE 4 OF THE LOW-INCOME ENERGY EFFICIENCY STANDARDIZATION PROJECT

This ruling approves a revised schedule for Phase 4 of the Low Income Energy Efficiency (LIEE) Standardization Project, as proposed by the joint utilities. The joint utilities are: Pacific Gas and Electric Company, Southern California Edison Company, Southern California Gas Company and San Diego Gas & Electric Company.

On January 28, 2003, I issued a ruling approving an augmentation of the budget for Phase 4 of the Low Income Energy Efficiency (LIEE) Standardization Project and additions to the Phase 4 work plan, as proposed by the joint utilities. Attached to that ruling was a revised schedule for completing Phase 4, which was presented under Section IV of Attachment 1 to that ruling.

At my request, the Standardization Project Team had submitted a revised schedule to the Energy Division that included completion dates for tasks 13-16.  Energy Division inadvertently submitted an outdated version of the schedule to me, which then was attached to my former ruling.  After my ruling issued on January 28th, Energy Division realized its error and submitted the correct revised schedule to me.

Accordingly, the correct revised schedule for Phase 4, as presented in Attachment 1, is adopted.

Dated February 24, 2003, at San Francisco, California.

/s/ CARL WOOD

Carl Wood Assigned Commissioner

Attachment 1

Schedule for Remaining Phase 4 Tasks (Revised January 24, 2003)

| Task and Milestone | Completion Date |
| --- | --- |
| Task 6. Analyze On-Site Data Submit Preliminary Survey Results to Standardization Team Standardization Team Meetings re NGAT Survey Results Complete Data Analysis | January 31, 2003 February 2003 (tbd) February 28, 2003 |
| Task 7. Prepare Phase 4 Report Submit Draft Survey Report to Standardization Team Standardization Team Meetings Submit Final Survey Report Draft Report to Public Final Report to Commission | March 10, 2003 March 2003 (tbd) March 25, 2003 April 1, 2003 May 5, 2003 |
| Task 8. Meetings, Workshops and Reply Comments Workshops on Draft NGAT Survey Report (North and South) | April 2003 (tbd) |
| Task 9. Develop Recommendations for Pre-Approval Policies Develop draft recommendations Distribute draft recommendations to public Submit final recommendations to Commission | March 15, 2003 April 1, 2003 May 5, 2003 |
| Task 10. Assess Current LIEE Measures Send Preliminary Results to Utilities Meet in San Francisco re Preliminary Results File Results | March 10, 2003 March, 2003 (tbd) April 1, 2003 |
| Task 13. Revise WIS and P&P Manuals for PY2003 | January 31, 2003 |
| Task 14. Complete Final Natural Gas Appliance CO Testing Standards and Procedures File new Appliance CO Testing Standards and Procedures Revise LIEE WIS Manual and Policy & Procedures Manual to reflect Gas Appliance CO Testing Standards and Procedures | 45 days after Commission Decision adopting updated Appliance CO testing policy 30 days from Commission decision adopting of new Appliance CO Testing Procedures |
| Task 15. Develop Statewide User Guide for Cost-Effectiveness Workbook | 45 days after Commission decision approving Phase 4 budget augmentation request |
| Task 16. CPUC Staff Project Briefings and Orientation | Throughout 2003 |

# CERTIFICATE OF SERVICE

I certify that I have by electronic mail sent to the parties of which an electronic mail address has been provided, this day served a true copy of the original attached ASSIGNED COMMISSIONER’S RULING REVISING THE SCHEDULE FOR PHASE 4 OF THE LOW-INCOME ENERGY EFFICIENCY STANDARDIZATION PROJECT on all parties of record for proceedings A.02-07-001, et al. or their attorneys of record.

Dated February 24, 2003, at San Francisco, California.

/s/ SUSIE TOY

Susie Toy

# NOTICE

Parties should notify the Process Office, Public Utilities Commission, 505 Van Ness Avenue, Room 2000, San Francisco, CA  94102, of any change of address to insure that they continue to receive documents.  You must indicate the proceeding number on the service list on which your name appears.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The Commission’s policy is to schedule hearings (meetings, workshops, etc.) in locations that are accessible to people with disabilities.  To verify that a particular location is accessible, call:  Calendar Clerk (415) 703-1203.

If specialized accommodations for the disabled are needed, e.g., sign language interpreters, those making the arrangements must call the Public Advisor at (415) 703-2074, TTY 1-866-836-7825 or (415) 703-5282 at least three working days in advance of the event.

sesco@optonline.net

wally.kolberg@swgas.com

dnorris@sppc.com

tgardner@sppc.com

fspasaro@semprautilities.com

wallis@winegardenergy.com

Mcart108@earthlink.net

arago@qcsca.com

caseadmin@sce.com

jennifer.hasbrouck@sce.com

kswitzer@scwater.com

kswitzer@scwater.com

manifold@pobox.com

gbaker@sempra.com

troberts@sempra.com

ywhiting@sdge.com

wparker@baprc.com

bfinkelstein@turn.org

elaine.duncan@verizon.com

rudy.reyes@verizon.com

mlm@cpuc.ca.gov

rcc@cpuc.ca.gov

lifcentral@lif.org

ecl8@pge.com

smalllecs@cwclaw.com

mschreiber@cwclaw.com

dfc2@pge.com

sdg6@pge.com

askaff@energy-law-group.com

irina@ideasarecheap.com

gferris@ski-kirkwood.com

jsnyder@housingca.org

bburt@macnexus.org

hodgesjl@pacbell.net

les.ueoka@verizon.com

dan@meek.net

marisa.decristoforo@pacificorp.com

rateca@avistacorp.com

barbalex@ctel.net

channon@aarp.org

bairda@ncs.com

ed.gieseking@swgas.com

bridget.branigan@swgas.com

mstrumwasser@strumwooch.com

Crudshagen@socalgas.com

parkhijf@sce.com

Michael_Berberet@ncs.com

mmoore@sempra.com

drrogers@semprautilities.com

bob@rer.com

fred@rer.com

brenda@rer.com

alanwoo@earthlink.net

eddie@proteusinc.org

pk@utilitycostmanagement.com

fosterbc@sce.com

jpeck@semprautilities.com

ira@cpuc.ca.gov

ecl8@pge.com

darleneclark@att.com

jscancarelli@flk.com

barbara@rhainc.com

ralf1241a@cs.com

rdeangelis@energy-law-group.com

chrism@mid.org

fwmonier@tid.org

blaising@braunlegal.com

energy@directapps.com

ldelacruz@aarp.org

lvictor@cal-neva.org

lvictor@cal-neva.org

MICCICHE@LACOOPERATIVA.ORG

mer@cpuc.ca.gov

gsanchez@rhainc.com

gsanchez@rhainc.com

mjuarez@riversidedpss.org

alanwoo@earthlink.net

paul.white@fresnoeoc.org

or10sia@aol.com

bam@cpuc.ca.gov

cxw@cpuc.ca.gov

dlw@cpuc.ca.gov

cpe@cpuc.ca.gov

gil@cpuc.ca.gov

imw@cpuc.ca.gov

jst@cpuc.ca.gov

jhe@cpuc.ca.gov

wbb@cpuc.ca.gov

kdg@cpuc.ca.gov

lam@cpuc.ca.gov

mzr@cpuc.ca.gov

meg@cpuc.ca.gov

rmb@cpuc.ca.gov

spc@cpuc.ca.gov

sjr@cpuc.ca.gov

tjt@cpuc.ca.gov

gottstein@volcano.net

zca@cpuc.ca.gov

tdayonot@csd.ca.gov

# Footnotes

The standardization Project Team consists of the joint utilities and their technical consultants.  Energy Division assists in coordinating the effort.  Per Commission direction, the project team obtains public input before submitting final recommendations to the Commission.