## ESA Table 1
Energy Savings Assistance Program Table 1 - Expenses
Southern California Edison
Through June 2019
| Authorized Budget [1] |  |  | Current Month Expenses |  |  | Year to Date Expenses |  |  | % of Budget Spent YTD
ESA Program: | Electric | Gas | Total | Electric | Gas | Total | Electric | Gas | Total | Electric | Gas | Total
Energy Efficiency
Appliances | 21628600 |  | 21628600 | 933792.7025 |  | 933792.7025 | 7457647.9875 |  | 7457647.9875 | 34.48% |  | 34.48%
Domestic Hot Water | 31348 |  | 31348 | 1516.25 |  | 1516.25 | 11130 |  | 11130 | 35.5% |  | 35.5%
Enclosure | 218022 |  | 218022 | 5086.67 |  | 5086.67 | 54234.52 |  | 54234.52 | 24.88% |  | 24.88%
HVAC | 24897305 |  | 24897305 | 2233868.812 |  | 2233868.812 | 15551896 |  | 15551896 | 62.46% |  | 62.46%
Maintenance | 100220 |  | 100220 | 0 |  | 0 | 0 |  | 0 | 0% |  | 0%
Lighting | 1013054 |  | 1013054 | 721644.6454 |  | 721644.6454 | 4776488.2899 |  | 4776488.2899 | 471.5% |  | 471.5%
Miscellaneous | 2631912 |  | 2631912 | 419571.27 |  | 419571.27 | 3005771.27 |  | 3005771.27 | 114.2% |  | 114.2%
Customer Enrollment | 4489283 |  | 4489283 | 579987.5 |  | 579987.5 | 3586993.5 |  | 3586993.5 | 79.9% |  | 79.9%
In Home Education | 1457578 |  | 1457578 | 166420 |  | 166420 | 978310 |  | 978310 | 67.12% |  | 67.12%
Pilot | 0 |  | 0 |  |  |  | 14861.5 |  | 14861.5
Energy Efficiency TOTAL | 56467322 |  | 56467322 | 6320532.5024 |  | 6320532.5024 | 35437333.0674 |  | 35437333.0674 | 62.76% |  | 62.76%
Training Center | 539344 |  | 539344 | 12477.62 |  | 12477.62 | 74646.65 |  | 74646.65 | 13.84% |  | 13.84%
Inspections | 1151406 |  | 1151406 | 112547.22 |  | 112547.22 | 557492.58 |  | 557492.58 | 48.42% |  | 48.42%
Marketing and Outreach [3] | 950000 |  | 950000 | 817777.25 |  | 817777.25 | 1060219.72 |  | 1060219.72 | 111.6% |  | 111.6%
Statewide Marketing Education and Outreach | 0 |  | 0 | 0 |  |  | 0 |  | 0
Measurement and Evaluation Studies | 91250 |  | 91250 | 0 |  | 0 | 95517.37 |  | 95517.37 | 104.7% |  | 104.7%
Regulatory Compliance | 478313 |  | 478313 | 45625.95 |  | 45625.95 | 280478.08 |  | 280478.08 | 58.64% |  | 58.64%
General Administration | 3879027 |  | 3879027 | 211883.29 |  | 211883.29 | 1922663.15 |  | 1922663.15 | 49.57% |  | 49.57%
CPUC Energy Division | 60000 |  | 60000 | 76457.71 |  | 76457.71 | 80218.73 |  | 80218.73 | 133.7% |  | 133.7%
TOTAL PROGRAM COSTS [2] | 63616662 |  | 63616662 | 7597301.5424 |  | 7597301.5424 | 39508569.3474 |  | 39508569.3474 | 62.1% |  | 62.1%
Funded Outside of ESA Program Budget
Indirect Costs |  |  |  | 96380 |  | 96380 | 600666 |  | 600666
NGAT Costs
[1] Reflects the authorized 2019 budget in D.16-11-022 and updated via Resolution E-4885 addressing conforming AL 3585-E and supplemental AL 3585-E-A. Total authorized budget in 2019 is $81,481,677; the total amount of $63,616,662 excludes the total authorized unspent funds of $17,865,015 captured in ESA Table 1A. The recently authorized budget approved in SCE’s Mid-Cycle Update AL 3824-E on January 4, 2019 has not been incorporated into the May Monthly report.
[2] Financial data for Energy Efficiency total monthly and year-to-date expenses are obtainted from EMAPS; financial data for Training Center, Inspections, Marketing & Outreach, Measurement & Evaluation Studies, Regulatory Compliance, General Administration, and CPUC Energy Division monthly and year-to-date expenses are obtained from SAP. Expenses for categories authorized to utilize unspent funds are not included in the table, refer to ESA Table 1A.
[X] Please indicate whether authorized budget includes shifted funds from previous years and/or prior program cycles. (Yes or No ) If yes, please specify amount, date fund-shifting activity occurred, date of fund-shifting request and related approval is applicable.
[3] Financial data for Marketing and Outreach includes a credit received as accounting adjustments in May.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## ESA Table 1A
Energy Savings Assistance Program Table 1A - Expenses Funded From 2009-2016 Unspent ESA Program Funds
Southern California Edison
Through June 2019
| Authorized Budget [1] |  |  | Current Month Expenses |  |  | Year to Date Expenses |  |  | % of Budget Spent YTD
ESA Program: | Electric | Gas | Total | Electric | Gas | Total | Electric | Gas | Total | Electric | Gas | Total
Energy Efficiency
Additional Regulatory Compliance Costs | 93750 |  | 93750 | 0 |  | 0 |  |  | 0 | 0% |  | 0%
Leveraging - CSD | 1000000 |  | 1000000 | 0 |  | 0 | 0 |  | 0 | 0% |  | 0%
Climate Zone 13 Central AC and AC related measures | 6666260 |  | 6666260 | 1059308.488 |  | 1059308.488 | 4233899 |  | 4233899 | 63.51% |  | 63.51%
HE Clothes Washer | 3318844 |  | 3318844 | 0 |  | 0 | 0 |  | 0 | 0% |  | 0%
Multi-Family Common Area Measures | 4500000 |  | 4500000 | 0 |  | 0 | 0 |  | 0 | 0% |  | 0%
Powerstrip Tier II | 2286161 |  | 2286161 | 202232.14 |  | 202232.14 | 1270379.45 |  | 1270379.45 | 55.57% |  | 55.57%
TOTAL UNSPENT PROGRAM COSTS [2] | 17865015 |  | 17865015 | 1261540.628 |  | 1261540.628 | 5504278.45 |  | 5504278.45 | 30.81% |  | 30.81%
[1] Reflects the authorized 2019 budget for unspent categories (i.e. new ESA program measures and directives) in D.16-11-022 and updated via Resolution E-4885 addressing conforming AL 3585-E and supplemental AL 3585-E.
[2] Financial data for monthly and year-to-date expenses for Additional Regulatory Compliance Costs category are obtained from SAP; financial data for monthly and year-to-date expenses for remaining categories are obtainted from EMAPS.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## ESA Table 2
Energy Savings Assistance Program Table 2
Southern California Edison
Through June 2019
| ESA Program (Summary)Total | [6 empty] | ESA Program (First Touch Homes Treated) | [7 empty] | ESA Program (Re-Treated Homes/Go Backs) | [6 empty] | ESA Program (Aliso Canyon - SCG & SCE) [6]
|  | Year-To-Date Completed & Expensed Installation | [6 empty] | Year-To-Date Completed & Expensed Installation | [7 empty] | Year-To-Date Completed & Expensed Installation | [6 empty] | Year-To-Date Completed & Expensed Installation
Measures | Units | Quantity Installed | kWh [4] (Annual) | kW [4] (Annual) | Therms [4] (Annual) | Expenses [5] ($) | % of Expenditure | Units | Quantity Installed | kWh [4] (Annual) | kW [4] (Annual) | Therms [4] (Annual) | Expenses [5] ($) | % of Expenditure |  | Units | Quantity Installed | kWh [4] (Annual) | kW [4] (Annual) | Therms [4] (Annual) | Expenses [5] ($) | % of Expenditure | Units | Quantity Installed | kWh [4] (Annual) | kW [4] (Annual) | Therms [4] (Annual) | Expenses [5] ($) | % of Expenditure
Appliances |  | (K+S) | (L+T) | (M+U) | (N+V) | (O+W)
New - High Efficiency Clothes Washer | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0% |  | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
Refrigerators | Each | 7070 | 4060178.26 | 489.3451 |  | 7457648 | 18.22% | Each | 5904 | 3392319.02 | 408.8499 |  | 6221047.5675 | 15.2% |  | Each | 1166 | 667859.24 | 80.4952 |  | 1236600.42 | 3.021% | Each | 6197 | 3563564.5 | 429.4848 |  | 6526067.695 | 15.95%
Microwaves | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0% |  | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
Domestic Hot Water
Water Heater Blanket | Home | 2 | 352 | 0.041436 |  | 102 | 0.0002492% | Home | 2 | 352 | 0.041436 |  | 102 | 0.0002492% |  | Home | 0 | 0 | 0 |  | 0 | 0% | Home | 2 | 352 | 0.041436 |  | 102 | 0.0004699%
Low Flow Shower Head | Home | 201 | 35051.67 | 4.1418 |  | 8522 | 0.02082% | Home | 194 | 33819.67 | 3.9964 |  | 8182 | 0.01999% |  | Home | 7 | 1232 | 0.14544 |  | 340 | 0.0008308% | Home | 184 | 31760.9 | 3.7536 |  | 7689.75 | 0.01814%
Water Heater Pipe Insulation | Home | 13 | 1924.86 | 0.22704 |  | 380.5 | 0.0009297% | Home | 13 | 1924.86 | 0.22704 |  | 380.5 | 0.0009297% |  | Home | 0 | 0 | 0 |  | 0 | 0% | Home | 12 | 1840.86 | 0.21714 |  | 360.75 | 0.0005459%
Faucet Aerator | Home | 185 | 32197.26 | 3.8225 |  | 2125.5 | 0.005193% | Home | 178 | 30972.26 | 3.6769 |  | 2034.5 | 0.004971% |  | Home | 7 | 1225 | 0.14555 |  | 91 | 0.0002223% | Home | 169 | 29353.86 | 3.4847 |  | 1976 | 0.004671%
Water Heater Repair/Replacement | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0% |  | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
Thermostatic Shower Valve | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0% |  | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
New - Combined Showerhead/TSV | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0% |  | Each | 0 | 0 | 0 | 0 | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
New - Heat Pump Water Heater | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0.1038% |  | Each | 0 | 0 | 0 | 0 | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
New - Tub Diverter/ Tub Spout | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0.02439% |  | Each | 0 | 0 | 0 | 0 | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
New - Thermostat-controlled Shower Valve | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0% |  | Each | 0 | 0 | 0 | 0 | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
Enclosure
Air Sealing / Envelope [1] | Home | 369 | -143989.23 | -62.2987 |  | 44253.52 | 0.1081% | Home | 359 | -137125.23 | -58.5745 |  | 42484.42 | 0.1038% |  | Home | 10 | -6864 | -3.7243 |  | 1769.1 | 0.004323% | Home | 331 | -132781.33 | -60.3772 |  | 39399.92 | 0.1141%
Caulking | Home | 0 | 0 | 0 |  | 0 | 0% | Home | 0 | 0 | 0 |  | 0 | 0% |  | Home | 0 | 0 | 0 |  | 0 | 0% | Home | 0 | 0 | 0 |  | 0 | 0%
Attic Insulation | Home | 5 | 0 | 0 |  | 9981 | 0.02439% | Home | 5 | 0 | 0 |  | 9981 | 0.02439% |  | Home | 0 | 0 | 0 |  | 0 | 0% | Home | 4 | 0 | 0 |  | 7731 | 0.01889%
HVAC
FAU Standing Pilot Conversion | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0% |  | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
Furnace Repair/Replacement | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0% |  | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
Room A/C Replacement | Each | 425 | -130389.55 | -20.0714 |  | 378335.47 | 0.9244% | Each | 319 | -98253.37 | -15.1231 |  | 284192.03 | 0.6944% |  | Each | 106 | -32136.18 | -4.9483 |  | 94143.44 | 0.23% | Each | 238 | -73796.7 | -11.3408 |  | 206555.0525 | 0.4284%
Central A/C replacement | Each | 2826 | 1059153.5203 | 141.0931 |  | 12755519.6625 | 31.17% | Each | 2325 | 880530.9965 | 115.4876 |  | 10399215.7325 | 25.41% |  | Each | 501 | 178622.5238 | 25.6055 |  | 2356303.93 | 5.757% | Each | 1316 | 505025.6432 | 63.7465 |  | 5668084.9425 | 16.72%
Heat Pump Replacement | Each | 112 | 144942.02 | 64.8133 |  | 437353.875 | 1.069% | Each | 98 | 125501.12 | 56.5628 |  | 380876.5825 | 0.9306% |  | Each | 14 | 19440.9 | 8.2505 |  | 56477.2925 | 0.138% | Each | 74 | 91832.57 | 41.7547 |  | 282146.7375 | 1.034%
Evaporative Cooler (Replacement) | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0% |  | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
Evaporative Cooler (Installation) | Each | 5254 | 3173775.43 | 489.6788 |  | 5577575.8 | 13.63% | Each | 4511 | 2724884.95 | 420.4255 |  | 4788194.54 | 11.7% |  | Each | 743 | 448890.48 | 69.2533 |  | 789381.26 | 1.929% | Each | 4122 | 2487588.58 | 383.7623 |  | 4362389.1775 | 12.45%
Duct Testing and Sealing | Home | 2717 | 62046.62 | 0.8862 |  | 637010 | 1.556% | Home | 2236 | 52988.15 | 0.7507 |  | 528180 | 1.291% |  | Home | 481 | 9058.47 | 0.1355 |  | 108830 | 0% | Home | 1280 | 42700.64 | 0.7872 |  | 316090 | 0.9675%
New - Energy Efficient Fan Control | Home | 0 | 0 | 0 |  | 0 | 0% | Home | 0 | 0 | 0 |  |  | 0% |  | Home | 0 | 0 | 0 |  |  | 0% | Home | 0 | 0 | 0 |  | 0 | 0%
New - Prescriptive Duct Sealing | Home | 0 | 0 | 0 |  | 0 | 0% | Home | 0 | 0 | 0 |  |  | 0% |  | Home | 0 | 0 | 0 |  |  | 0% | Home | 0 | 0 | 0 |  | 0 | 0%
New - High Efficiency Forced Air Unit (HE FAU) | Home | 0 | 0 | 0 |  | 0 | 0% | Home | 0 | 0 | 0 |  |  | 0% |  | Home | 0 | 0 | 0 |  |  | 0% | Home | 0 | 0 | 0 |  | 0 | 0%
New - A/C Time Delay | Home | 0 | 0 | 0 |  | 0 | 0% | Home | 0 | 0 | 0 |  |  | 0% |  | Home | 0 | 0 | 0 |  |  | 0% | Home | 0 | 0 | 0 |  | 0 | 0%
Maintenance
Furnace Clean and Tune | Home | 0 | 0 | 0 |  | 0 | 0% | Home | 0 | 0 | 0 |  | 0 | 0% |  | Home | 0 | 0 | 0 |  |  | 0% | Home | 0 | 0 | 0 |  | 0 | 0%
Central A/C Tune up | Home | 0 | 0 | 0 |  | 0 | 0% | Home | 0 | 0 | 0 |  | 0 | 0% |  | Home | 0 | 0 | 0 |  |  | 0% | Home | 0 | 0 | 0 |  | 0 | 0%
Lighting
Compact Fluorescent Lights (CFL) [7] | Each | 114 | 1876.8 | 0.2389 |  | 824.8381 | 0.002015% | Each | 114 | 1876.8 | 0.2389 |  | 824.8381 | 0.002015% |  | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 19 | 309.3 | 0.0394 |  | 137.1653 | 0.0003351%
Torchiere [7] | Each | 1 | 95.76 | 0.0123 |  | 56.4734 | 0.000138% | Each | 1 | 95.76 | 0.0123 |  | 56.4734 | 0.000138% |  | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 1 | 95.76 | 0.0123 |  | 56.4734 | 0.000138%
Exterior Hard wired CFL fixtures [7] | Each | 11 | 385 | 0.0495 |  | 990 | 0.002419% | Each | 8 | 280 | 0.036 |  | 720 | 0.001759% |  | Each | 3 | 105 | 0.0135 |  | 270 | 0.0006597% | Each | 4 | 140 | 0.018 |  | 360 | 0.0008796%
Exterior Hard wired LED fixtures | Each | 264 | 5600.9186 | 0.2275 |  | 22904.89 | 0.05597% | Each | 190 | 4308.9849 | 0.2002 |  | 16866.34 | 0.04121% |  | Each | 74 | 1291.9337 | 0.0273 |  | 6038.55 | 0.01475% | Each | 114 | 3410.2136 | 0.2275 |  | 10588.9 | 0.02384%
Occupancy Sensor | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0% |  | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
LED Night Lights | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0% |  | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
New - LED Diffuse Bulb (60W Replacement) | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  |  | 0% |  | Each | 0 | 0 | 0 |  |  | 0% | Each | 0 | 0 | 0 |  | 0 | 0%
New - LED Reflector Bulb | Each | 6307 | 133757.8074 | 16.3843 |  | 52658.1018 | 0.1287% | Each | 5718 | 121146.7549 | 14.8537 |  | 47752.9618 | 0.1167% |  | Each | 589 | 12611.0525 | 1.5305 |  | 4905.14 | 0.01199% | Each | 6038 | 127840.0355 | 15.6815 |  | 50558.5218 | 0.1235%
New - LED Reflector Downlight Retrofit Kits | Each | 0 | 0 | 0 |  | 0 | 0% | Each | 0 | 0 | 0 |  |  | 0% |  | Each | 0 | 0 | 0 |  |  | 0% | Each | 0 | 0 | 0 |  |  | 0%
New - LED A-Lamps | Each | 401314 | 15570069.564 | 1880.9218 |  | 3703903.0698 | 9.05% | Each | 315667 | 12237943.5508 | 1471.784 |  | 2907151.9066 | 7.103% |  | Each | 85647 | 3332126.0132 | 409.1379 |  | 796751.1632 | 1.947% | Each | 365473 | 14110644.9281 | 1696.7276 |  | 3365828.5125 | 8.224%
New - LED Torchiere | Each | 15522 | 1087981.5481 | 126.2722 |  | 995150.9168 | 2.432% | Each | 12929 | 905589.6711 | 104.335 |  | 829054.5334 |  | 995150.9168 | Each | 2593 | 182391.877 | 21.9372 |  | 166096.3834 | 0.4058% | Each | 14806 | 1035991.4556 | 120.2263 |  | 949156.3498 | 2.319%
Miscellaneous
Pool Pumps | Each | 981 | 1109697 | 348.9646 |  | 1181681.9402 | 2.887% | Each | 851 | 959992 | 301.8819 |  | 1030696.2563 | 2.518% |  | Each | 130 | 149705 | 47.0827 |  | 150985.6839 | 0.3689% | Each | 771 | 869652 | 273.4511 |  | 914950.0734 | 2.236%
Smart Power Strips - Tier 1 | Each | 44474 | -770849 | -104.6726 |  | 1824089.3343 | 4.457% | Each | 34461 | -598801.7 | -81.3106 |  | 1413467.7158 | 3.454% |  | Each | 10013 | -172047.3 | -23.3621 |  | 410621.6185 | 1.003% | Each | 43050 | -749248.8 | -101.7396 |  | 1765793.5006 | 4.315%
New - Smart Power Strips - Tier 2 | Each | 21624 | 2984251.4 | 584.0381 |  | 1270379.4467 | 3.104% | Each | 17319 | 2386152.6 | 465.62 |  | 1017572.2601 | 2.486% |  | Each | 4305 | 598098.8 | 118.418 |  | 252807.1866 | 0.6177% | Each | 19696 | 2702494.6 | 522.9533 |  | 1156903.4886 | 2.827%
Pilots
Customer Enrollment
Outreach & Assessment | Home | 47153 | 0 | 0 |  | 3586993.5 | 8.764% | Home | 37720 | 0 | 0 |  | 2913900.5 | 7.12% |  | Home | 9433 | 0 | 0 |  | 673093 | 1.645% | Home | 41924 | 0 | 0 |  | 3130889 | 7.65%
In-Home Education | Home | 40094 | 0 | 0 |  | 978310 | 2.39% | Home | 31988 | 0 | 0 |  | 781040 | 1.908% |  | Home | 8106 | 0 | 0 |  | 197270 | 0.482% | Home | 35608 | 0 | 0 |  | 871890 | 2.13%
Total Savings/Expenditures |  |  | 28418109.6584 | 3964.1156 |  | 40926749.8261 |  |  | 155980 | 155980 | 3213.9722 |  | 33623974.658 |  |  |  |  | 5391610.8102 | 750.1434 |  | 7302775.1681 |  |  |  | 24648771.0161 | 3382.9117 |  | 29635705.0104
Total Households Weatherized [2] | Home | 368 | [5 empty] | Home | 368 | [6 empty] | Home | 0 | [5 empty] | Home | 330
Households Treated | Total (K+S) | [6 empty] | First Touches | [7 empty] | Re-treated Homes/Go-Backs | [6 empty] | Aliso Canyon
- Single Family Households Treated | Home | 29515 | [5 empty] | Home | 22866 | [6 empty] | Home | 6649 | [5 empty] | Home | 25673
- Multi-family Households Treated | Home | 11010 | [5 empty] | Home | 9443 | [6 empty] | Home | 1567 | [5 empty] | Home | 10828
- Mobile Homes Treated | Home | 3047 | [5 empty] | Home | 2401 | [6 empty] | Home | 646 | [5 empty] | Home | 2721
Total Number of Households Treated | Home | 43572 | [5 empty] | Home | 34710 | [6 empty] | Home | 8862 | [5 empty] | Home | 39222
# Eligible Households to be Treated for PY [3] | Home | 95168 | [5 empty] | Home | 95168 | [6 empty] | Home | [6 empty] | Home
% of Households Treated | % | 45.78% | [5 empty] | % | 36.47% | [6 empty] | % | [6 empty] | %
- Master-Meter Households Treated | Home | 6446 | [5 empty] | Home | 5430 | [6 empty] | Home | 1016 | [5 empty] | Home | 6105
[1] Envelope and Air Sealing Measures may include outlet cover plate gaskets, attic access weatherization, weatherstripping - door, caulking and minor home repairs. Minor home repairs predominantly are door jamb repair / replacement, door repair, and window putty.
[2] Weatherization may consist of attic insulation, attic access weatherization, weatherstripping - door, caulking, & minor home repairs
[3] Based on Resolution E-4885 approving SCE’s Authorized CARE and ESA Programs Conforming AL 3585-E and Supplemental AL 3585-E-A filed in compliance with D.16-11-022.
[4] All savings are calculated based on Evergreen Economics “Impact Evaluation of the 2011 CA Low Income Energy Efficiency Program, Final Report.” August 30, 2013
[5] Costs exclude support costs that are included in Table 1; excludes costs for common area measures, refer to ESA Table 2B.
[6] Data for Aliso Canyon includes "First Touches and Re-Treatments".
[7] Expenses for fluorescent lighting reflect installations completed on or before December 31, 2017 and invoiced in 2018.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## ESA Table 2A
Energy Savings Assistance Program Table 2A
Southern California Edison
Through June 2019
| ESA Program (Summary)Total | [6 empty] | ESA Program - CSD Leveraging
|  | Year-To-Date Completed & Expensed Installation | [5 empty] | Year-To-Date Completed & Expensed Installation
Measures | Units | Quantity Installed | kWh [4] (Annual) | kW [4] (Annual) | Therms [4] (Annual) | Expenses ($) | % of Expenditure | Quantity Installed | kWh [4] (Annual) | kW [4] (Annual) | Therms [4] (Annual) | Expenses ($) | % of Expenditure
Appliances
High Efficiency Clothes Washer | Each | 0 | 0 | 0 | 0 | 0 | 0% | [5 empty] | 0%
Refrigerators | Each | 7070 | 4060178.26 | 489.3451 | 0 | 7457648 | 18.22% | [5 empty] | 0%
Microwaves | Each | 0 | 0 | 0 | 0 | 0 | 0% | [5 empty] | 0%
Domestic Hot Water
Water Heater Blanket | Home | 2 | 352 | 0.041436 |  | 102 | 0.0002492% | [5 empty] | 0%
Low Flow Shower Head | Home | 201 | 35051.67 | 4.1418 |  | 8522 | 0.02082% | [5 empty] | 0%
Water Heater Pipe Insulation | Home | 13 | 1924.86 | 0.22704 |  | 380.5 | 0.0009297% | [5 empty] | 0%
Faucet Aerator | Home | 185 | 32197.26 | 3.8225 |  | 2125.5 | 0.005193% | [5 empty] | 0%
Water Heater Repair/Replacement | Each | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
Thermostatic Shower Valve | Each | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
New - Combined Showerhead/TSV | Each | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
New - Heat Pump Water Heater | Each | 0 | 0 | 0 | 0 | 0 | 0% | [5 empty] | 0%
New - Tub Diverter/ Tub Spout | Each | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
New - Thermostat-controlled Shower Valve | Each | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
Enclosure
Air Sealing / Envelope [1] | Home | 369 | -143989.23 | -62.2987 |  | 44253.52 | 0.1081% | [5 empty] | 0%
Caulking | Home |  |  |  |  | 0 | 0% | [5 empty] | 0%
Attic Insulation | Home | 5 | 0 | 0 |  | 9981 | 0.02439% | [5 empty] | 0%
HVAC
FAU Standing Pilot Conversion | Each | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
Furnace Repair/Replacement | Each | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
Room A/C Replacement | Each | 425 | -130389.55 | -20.0714 |  | 378335.47 | 0.9244% | [5 empty] | 0%
Central A/C replacement | Each | 2826 | 1059153.5203 | 141.0931 |  | 12755519.6625 | 31.17% | [5 empty] | 0%
Heat Pump Replacement | Each | 112 | 144942.02 | 64.8133 |  | 437353.875 | 1.069% | [5 empty] | 0%
Evaporative Cooler (Replacement) | Each | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
Evaporative Cooler (Installation) | Each | 5254 | 3173775.43 | 489.6788 |  | 5577575.8 | 13.63% | [5 empty] | 0%
Duct Testing and Sealing | Home | 2717 | 62046.62 | 0.8862 |  | 637010 | 1.556% | [5 empty] | 0%
New - Energy Efficient Fan Control | Home | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
New - Prescriptive Duct Sealing | Home | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
New - High Efficiency Forced Air Unit (HE FAU) | Home | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
New - A/C Time Delay | Home | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
Maintenance
Furnace Clean and Tune | Home | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
Central A/C Tune up | Home | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
Lighting
Compact Fluorescent Lights (CFL) [7] | Each | 114 | 1876.8 | 0.2389 |  | 824.8381 | 0.002015% | [5 empty] | 0%
Torchiere [7] | Each | 1 | 95.76 | 0.0123 |  | 56.4734 | 0.05597% | [5 empty] | 0%
Exterior Hard wired CFL fixtures [7] | Each | 11 | 385 | 0.0495 |  | 990 | 0.000138% | [5 empty] | 0%
Exterior Hard wired LED fixtures | Each | 264 | 5600.9186 | 0.2275 |  | 22904.89 | 0% | [5 empty] | 0%
Occupancy Sensor | Each | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
LED Night Lights | Each | 0 | 0 | 0 |  | 0 | 0% | [5 empty] | 0%
New - LED Diffuse Bulb (60W Replacement) | Each | 0 | 0 | 0 |  | 0 | 0.1287% | [5 empty] | 0%
New - LED Reflector Bulb | Each | 6307 | 133757.8074 | 16.3843 |  | 52658.1018 | 0% | [5 empty] | 0%
New - LED Reflector Downlight Retrofit Kits | Each | 0 | 0 | 0 |  | 0 | 9.05% | [5 empty] | 0%
New - LED A-Lamps | Each | 401314 | 15570069.564 | 1880.9218 |  | 3703903.0698
New - LED Torchiere | Each | 15522 | 1087981.5481 | 126.2722 |  | 995150.9168 | 2.432% | [5 empty] | 0%
Miscellaneous
Pool Pumps | Each | 981 | 1109697 | 348.9646 |  | 1181681.9402 | 2.887% | [5 empty] | 0%
Smart Power Strips - Tier 1 | Each | 44474 | -770849 | -104.6726 |  | 1824089.3343 | 4.457% | [5 empty] | 0%
New - Smart Power Strips - Tier 2 | Each | 21624 | 2984251.4 | 584.0381 |  | 1270379.4467 | 3.104% | [5 empty] | 0%
Ancillary Services
Commissioning | Home | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Audit | Home | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Administration | Home | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Pilots
Customer Enrollment
Outreach & Assessment | Home | 47153 |  |  |  | 3586993.5 | 8.764% |  |  |  |  | 0 | 0%
In-Home Education | Home | 40094 |  |  |  | 978310 | 2.39% |  |  |  |  | 0 | 0% | `
Total Savings/Expenditures |  |  | 28418109.6584 | 3964.1157 |  | 40926749.8386 |  |  | 0 | 0 | 0 | 0 | 0%
Total Households Weatherized [2] | Home | 368
Households Treated |  | Total | [5 empty] | CSD MF Buildings Treated |  |  | Total
- Single Family Households Treated | Home | 29515
- Multi-family Households Treated | Home | 11010 | [5 empty] | - Multifamily
- Mobile Homes Treated | Home | 3047
Total Number of Households Treated | Home | 43572
# Eligible Households to be Treated for PY [3] | Home | 95168
% of Households Treated | % | 45.78%
- Master-Meter Households Treated | Home | 6446
[1] Envelope and Air Sealing Measures may include outlet cover plate gaskets, attic access weatherization, weatherstripping - door, caulking and minor home repairs. Minor home repairs predominantly are door jamb repair / replacement, door repair, and window putty.
[2] Weatherization may consist of attic insulation, attic access weatherization, weatherstripping - door, caulking, & minor home repairs
[3] Based on Resolution E-4885 approving SCE’s Authorized CARE and ESA Programs Conforming AL 3585-E and Supplemental AL 3585-E-A filed in compliance with D.16-11-022.
[4] All savings are calculated based on Evergreen Economics “Impact Evaluation of the 2011 CA Low Income Energy Efficiency Program, Final Report.” August 30, 2013
[5] Costs exclude support costs that are included in Table 1; excludes costs for common area measures, refer to ESA Table 2B.
[6] Data for Aliso Canyon includes "First Touches and Re-Treatments".
[7] Expenses for fluorescent lighting reflect installations completed on or before December 31, 2017 and invoiced in 2018.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## ESA Table 2B
Energy Savings Assistance Program Table 2B
Southern California Edison
Through June 2019
ESA Program - Multifamily Common Area [6]
Year-To-Date Completed & Expensed Installation
Measures | Units | Quantity Installed | kWh [4] (Annual) | kW [4] (Annual) | Therms [4] (Annual) | Expenses ($) | % of Expenditure
Appliances
High Efficiency Clothes Washer | Each
Refrigerators | Each
Microwaves | Each
Domestic Hot Water
Water Heater Blanket | Home
Low Flow Shower Head | Home
Water Heater Pipe Insulation | Home
Faucet Aerator | Home
Water Heater Repair/Replacement | Each
Thermostatic Shower Valve | Each
New - Combined Showerhead/TSV | Each
New - Heat Pump Water Heater | Each
New - Tub Diverter/ Tub Spout | Each
New - Thermostat-controlled Shower Valve | Each
Enclosure
Air Sealing / Envelope [1] | Home
Caulking | Home
Attic Insulation | Home
HVAC
FAU Standing Pilot Conversion | Each
Furnace Repair/Replacement | Each
Room A/C Replacement | Each
Central A/C replacement | Each
Heat Pump Replacement | Each
Evaporative Cooler (Installation) | Each
Duct Testing and Sealing | Home
New - Energy Efficient Fan Control | Home
New - Prescriptive Duct Sealing | Home
New - High Efficiency Forced Air Unit (HE FAU) | Home
New - A/C Time Delay | Home
Maintenance
Furnace Clean and Tune | Home
Central A/C Tune up | Home
Lighting
Occupancy Sensor | Each
LED Night Lights | Each
New - LED Diffuse Bulb (60W Replacement) | Each
New - LED Reflector Bulb | Each
New - LED Reflector Downlight Retrofit Kits | Each
New - LED A-Lamps | Each
Miscellaneous
Pool Pumps | Each
Smart Power Strips - Tier 1 | Each
New - Smart Power Strips - Tier 2 | Each
Ancillary Services
Administration [2] | Home
Audit | Home
Commissioning [3] | Home
Pilots
Customer Enrollment
Outreach & Assessment | Home |  |  |  |  | 0
In-Home Education | Home |  |  |  |  | 0 |  | `
Total Savings/Expenditures |  |  | 0 | 0 | 0 | 0
Total Multifamily Buildings Weatherized [5]
Multifamily Buildings Treated | Total
- Multifamily
[1] Envelope and Air Sealing Measures may include outlet cover plate gaskets, attic access weatherization, weatherstripping - door, caulking and minor home repairs. Minor home repairs predominantly are door jamb repair / replacement, door repair, and window putty.
[2] Per D.16-11-022 at p.210, the CPUC imposes a cap of 10% of ESA Program funds for administrative activities and a ceiling of 20% for direct implementation non-incentive costs.
[3] Refers to optimizing the installation of the measure installed such as retrofitting pipes, etc.
[4] All savings are calculated based on Evergreen Economics “Impact Evaluation of the 2011 CA Low Income Energy Efficiency Program, Final Report.” August 30, 2013
[5] Weatherization may consist of attic insulation, attic access weatherization, weatherstripping - door, caulking, & minor home repairs
[6] Applicable to Deed-Restricted, government and non-profit owned multi-family buildings described in D.16-11-022 where 65% of tenants are income eligible based on CPUC income requirements of at or below 200% of the Federal Poverty Guidelines.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## ESA Table 3
Energy Savings Assistance Program Table 3 Energy Savings and Average Bill Savings per Treated Home/Common Area
Southern California Edison
Through June 2019
ESA Program
Annual kWh Savings | 28418110
Annual Therm Savings
Lifecycle kWh Savings | 382813774
Lifecycle Therm Savings
Current kWh Rate | 0.13
Current Therm Rate
Average 1st Year Bill Savings / Treated households | 84.78
Average Lifecycle Bill Savings / Treated Household | 1142.1
ESA Program - CSD Leveraging
Annual kWh Savings
Annual Therm Savings
Lifecycle kWh Savings
Lifecycle Therm Savings
Current kWh Rate | 0
Current Therm Rate | 0
Average 1st Year Bill Savings / Treated Households | 0
Average Lifecycle Bill Savings / Treated Household | 0
ESA Program - Multifamily Common Area
Annual kWh Savings | 7504185.0313
Annual Therm Savings
Lifecycle kWh Savings | 102898459.8958
Lifecycle Therm Savings
Current kWh Rate | 0.13
Current Therm Rate
Average 1st Year Bill Savings / Treated Buildings | 90.0031
Average Lifecycle Bill Savings / Treated Buildings | 1234.136
Summary - ESA Program/CSD Leveraging/ Multifamily Common Area
Annual kWh Savings
Annual kW Savings
Annual Therm Savings
Lifecycle kWh Savings
Lifecycle Therm Savings
Current kWh Rate | 0
Current Therm Rate | 0
Average 1st Year Bill Savings / Treated households and Buildings | 0
Average Lifecycle Bill Savings / Treated Household and Buildings | 0
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## ESA Table 4A
Energy Savings Assistance Program Table 4A - Homes/Buildings Treated
Southern California Edison
Through June 2019
ESA Program
| Eligible Households* |  |  | Households Treated YTD
County | Rural [1] | Urban | Total | Rural | Urban | Total
FRESNO | 0 | 520 | 520 | 0 | 0 | 0
IMPERIAL | 188 | 0 | 188 | 0 | 0 | 0
INYO | 1271.4077 | 4.5923 | 1276 | 4 | 0 | 4
KERN | 17280.8954 | 13069.1046 | 30350 | 771 | 1 | 772
KINGS | 8357 | 0 | 8357 | 184 | 0 | 184
LOS ANGELES | 3064.1424 | 541091.8576 | 544156 | 222 | 18527 | 18749
MADERA | 0 | 3 | 3 | 0 | 0 | 0
MONO | 1567.6472 | 0.3528 | 1568 | 1 | 0 | 1
ORANGE | 0.40275 | 201376.5972 | 201377 | 0 | 5242 | 5242
RIVERSIDE | 93007.7211 | 97623.2789 | 190631 | 1150 | 6070 | 7220
SAN BERNARDINO | 36376.8584 | 189139.1416 | 225516 | 1115 | 8223 | 9338
SAN DIEGO | 1 | 0 | 1 | 0 | 0 | 0
SANTA BARBARA | 0 | 18004 | 18004 | 0 | 31 | 31
TULARE | 45643.4623 | 13442.5377 | 59086 | 1026 | 576 | 1602
TUOLUMNE | 0 | 0 | 0 | 0 | 0 | 0
VENTURA | 2580.9757 | 63378.0243 | 65959 | 28 | 403 | 431
Total | 209339.513 | 1137652.487 | 1346992 | 4501 | 39073 | 43574
ESA Program - CSD Leveraging
Households Treated YTD
County |  |  |  | Rural | Urban | Total
0
0
Total |  |  |  | 0 | 0 | 0
ESA Program - Multifamily Common Area
Buildings Treated YTD
County |  |  |  | Rural | Urban | Total
0
0
Total |  |  |  | 0 | 0 | 0
[1] For IOU low income-related and Energy Efficiency reporting and analysis, the Goldsmith definition is applied.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.
* Estimated eligible households is updated using Athens Research dataset provided in March 2019.

## ESA Table 4B
Energy Savings Assistance Program Table 4B - Homes Unwilling / Unable to Participate
Southern California Edison
Through June 2019
ESA Program
Reason Provided
County | Customer Unwilling/Declined Program Measures | Customer Unavailable -Scheduling Conflicts | Hazardous Environment (unsafe/unclean) | Landlord Refused to Authorize Participation | Household Exceeds Allowable Limits | Unable to Provide Required Documentation | Other Infeasible/ Ineligible
Fresno | 0 | 0 | 0 | 0 | 0 | 0 | 0
Imperial | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inyo | 0 | 0 | 0 | 0 | 0 | 4 | 10
Kern | 1 | 5 | 0 | 45 | 9 | 94 | 276
Kings | 3 | 1 | 0 | 3 | 4 | 8 | 156
Los Angeles | 21 | 45 | 1 | 959 | 142 | 2143 | 8478
Madera | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mono | 0 | 0 | 0 | 2 | 0 | 0 | 0
Orange | 7 | 20 | 0 | 203 | 50 | 464 | 3361
Riverside | 43 | 64 | 0 | 368 | 84 | 385 | 2379
San Bernardino | 61 | 483 | 0 | 569 | 89 | 816 | 4234
Sandiego | 0 | 0 | 0 | 0 | 0 | 0 | 0
Santa Barbara | 0 | 0 | 0 | 0 | 3 | 0 | 36
Tulare | 14 | 33 | 0 | 11 | 9 | 58 | 911
Tuolumne | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ventura | 0 | 4 | 0 | 18 | 19 | 25 | 280
Total | 150 | 655 | 1 | 2178 | 409 | 3997 | 20121
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## ESA Table 5
Energy Savings Assistance Program Table 5 - Energy Savings Assistance Program Customer Summary
Southern California Edison
Through June 2019
ESA Program
Month | Gas & Electric |  |  |  | Gas Only |  |  |  | Electric Only |  |  |  | Total
| # of Household Treated by Month | (Annual) |  |  | # of Household Treated by Month | (Annual) |  |  | # of Household Treated by Month | (Annual) |  |  | # of Household Treated by Month | (Annual)
|  | Therm | kWh | kW |  | Therm | kWh | kW |  | Therm | kWh | kW |  | Therm | kWh | kW
January | [8 empty] | 4490 |  | 3556742 | 488 | 4490 |  | 3556742 | 488
February | [8 empty] | 10839 |  | 7504185.0313 | 1034.1193 | 10839 |  | 7504185.0313 | 1034.1193
March | [8 empty] | 19565 |  | 13159248.3848 | 1825.2092 | 19567 |  | 13159248.3848 | 1825.2092
April | [8 empty] | 23856 |  | 15990007.4525 | 2214.7244 | 23858 |  | 15990007.4525 | 2214.7244
May | [8 empty] | 36395 |  | 24177598.8584 | 3356.3504 | 36397 |  | 24177598.8584 | 3356.3504
June | [8 empty] | 43572 |  | 28418109.6584 | 3964.1091 | 43572 |  | 28418109.6584 | 3964.1091
July
August
September
October
November
December
YTD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43572 |  | 28418109.6584 | 3964.1091 | 43572 |  | 28418109.6584 | 3964.1091
YTD Total Energy Impacts for all fuel types should equal YTD energy impacts that are reported every month Table 2.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.
ESA Program - CSD Leveraging
| Gas & Electric |  |  |  | Gas Only |  |  |  | Electric Only |  |  |  | Total
Month
| # of Buildings Treated by Month | (Annual) |  |  | # of Household Treated by Month | (Annual) |  |  | # of Household Treated by Month | (Annual) |  |  | # of Household Treated by Month | (Annual)
|  | Therm | kWh | kW |  | Therm | kWh | kW |  | Therm | kWh | kW |  | Therm | kWh | kW
January
February
March
April
May
June
July
August
September
October
November
December
YTD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
YTD Total Energy Impacts for all fuel types should equal YTD energy impacts that are reported every month Table 2A.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.
ESA Program - Multifamily Common Area
Month | Gas & Electric |  |  |  | Gas Only |  |  |  | Electric Only |  |  |  | Total
| # of Buildings Treated by Month | (Annual) |  |  | # of Buildings Treated by Month | (Annual) |  |  | # of Buildings Treated by Month | (Annual) |  |  | # of Buildings Treated by Month | (Annual)
|  | Therm | kWh | kW |  | Therm | kWh | kW |  | Therm | kWh | kW |  | Therm | kWh | kW
January
February
March
April
May
June
July
August
September
October
November
December
YTD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
YTD Total Energy Impacts for all fuel types should equal YTD energy impacts that are reported every month Table 2B.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## ESA Table 6
Energy Savings Assistance Program Table 6 - Expenditures for Pilots and Studies
Southern California Edison
Through June 2019
| Authorized 2018 Funding |  |  | Current Month Expenses |  |  | Expenses Since January 1, 2018 |  |  | % of Budget Expensed
| Electric | Gas | Total | Electric | Gas | Total | Electric | Gas | Total | Electric | Gas | Total
Pilots
Programmable Controllable Thermostat |  |  | 0 |  |  | 0 |  |  | 0
Total Pilots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Studies
Rapid Feedback Research and Analysis |  |  | 0 |  |  | 0 |  |  | 0
Low Income Needs Assessment Study |  |  | 0 |  |  | 0 |  |  | 0
Load Impact Evaluation Study |  |  | 0 |  |  | 0 |  |  | 0
2017 Potential and Goals Study |  |  | 0 |  |  | 0 |  |  | 0
Total Studies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## ESA Table 7
Energy Savings Assistance Program Table 7
Southern California Edison
Through June 2019
Measures | Units | Received Refrigerator | Not eligible for Refrigerator due to Less than Six Occupants
Second Refrigerators | Each
Measures | Units | Households that Only Received Energy Education [1]
In-Home Energy Education | Home | 3799
Households for My Energy/My Account Platform [1]
Opt-Out | Already Enrolled | Opt-In
48876 | 1856 | 804
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## CARE Table 1
CARE Table 1 - CARE Program Expenses
Southern California Edison
Through June 2019
| Authorized Budget |  |  | Current Month Expenses |  |  | Year to Date Expenses[4][5] |  |  | % of Budget Spent YTD
CARE Program: | Electric | Gas | Total | Electric | Gas | Total | Electric | Gas | Total | Electric | Gas | Total
Outreach | 2684843 |  | 2684843 | 737791.9 |  | 737791.9 | 1397164.59 |  | 1397164.59 | 52.04% |  | 52.04%
Processing / Certification Re-certification | 800000 |  | 800000 | 66260 |  | 66260 | 264900.63 |  | 264900.63 | 33.11% |  | 33.11%
Post Enrollment Verification | 600000 |  | 600000 | 39346.3 |  | 39346.3 | 279060.01 |  | 279060.01 | 46.51% |  | 46.51%
IT Programming | 600000 |  | 600000 | 2010.4 |  | 2010.4 | 92529.48 |  | 92529.48 | 15.42% |  | 15.42%
Cooling Centers | 44562 |  | 44562 | 4612 |  | 4612 | 14825.5 |  | 14825.5 | 33.27% |  | 33.27%
Pilots/CHANGES Program [1] | 525000 |  | 525000 | 120203.3 |  | 120203.3 | 223198.68 |  | 223198.68 | 42.51% |  | 42.51%
Studies [2] | 150000 |  | 150000 | 0 |  | 0 | 0 |  | 0 | 0% |  | 0% | `
Regulatory Compliance | 542704 |  | 542704 | 21934.49 |  | 21934.49 | 196351.38 |  | 196351.38 | 36.18% |  | 36.18%
General Administration | 704529 |  | 704529 | 58055.69 |  | 58055.69 | 352745.87 |  | 352745.87 | 50.07% |  | 50.07%
CPUC Energy Division | 140000 |  | 140000 | 0 |  | 0 | 41543.29 |  | 41543.29 | 29.67% |  | 29.67%
SUBTOTAL MANAGEMENT COSTS [3] | 6791638 |  | 6791638 | 1050214.08 |  | 1050214.08 | 2862319.43 |  | 2862319.43 | 42.14% |  | 42.14%
CARE Rate Discount | 487221423 |  | 487221423 | 25474822.53 |  | 25474822.53 | 154061355.84 |  | 154061355.84 | 31.62% |  | 31.62%
TOTAL PROGRAM COSTS & CUSTOMER DISCOUNTS | 494013061 |  | 494013061 | 26525036.61 |  | 26525036.61 | 156923675.27 |  | 156923675.27 | 31.77% |  | 31.77%
Other CARE Rate Benefits
- DWR Bond Charge Exemption |  |  |  | 1617730.9799 |  | 1617730.9799 | 10540394.4506 |  | 10540394.4506
- CARE PPP Exemption |  |  |  | 1775323.0634 |  | 1775323.0634 | 11295356.8379 |  | 11295356.8379
- California Solar Initiative Exemption |  |  |  | 0 |  | 0 | 964538.9473 |  | 964538.9473
- kWh Surcharge Exemption |  |  |  | 0 |  | 0 | 0 |  | 0
Total Other CARE Rate Benefits |  |  |  | 3393054.0433 |  | 3393054.0433 | 22800290.2359 |  | 22800290.2359
Indirect Costs |  |  |  | 68463 |  | 68463 | 464033 |  | 464033
,
[1] Decision 15-12-047 transitioned from CHANGES pilot to CHANGES program and funding for the effort is captured herein.
[2] Reflects the Annual Eligibility Estimates prepared by Athens Research on behalf of the utilities. This efforts was formerly referenced in Measurement and Evaluation.
[3] Reflects the authorized funding per year in D.16-11-022 and updated via Resolution [E-4885] addressing Conforming AL [3585-E] and Supplemental Conforming AL [3585-E-A].
[4] Monthly and year-to-date expenses data was obtained from SAP database. Subtotal Management Costs for 2017 include Cooling Centers total costs.
[5] Total costs settled to prior cycle CARE accounting are not addressed in CARE Table 1.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## CARE Table 2
CARE Table 2 - Enrollment, Recertification, Attrition, & Penetration
Southern California Edison
Through June 2019
| New Enrollment | [9 empty] | Recertification[4] |  |  |  | Attrition (Drop Offs) [5] |  |  |  |  | Enrollment |  | Total CARE Participants | Estimated CARE Eligible | Penetration Rate % (W/X)
| Automatic Enrollment |  |  |  | Self-Certification (Income or Categorical) |  |  |  |  | Total New Enrollment (E+J) | Scheduled | Non-Scheduled (Duplicates) | Automatic | Total Recertification (L+M+N) | No Response [6] | Failed PEV | Failed Recertification | Other | Total Attrition (P+Q+R+S) | Gross (K+O) | Net Adjusted (K-T)
| Inter-Utility 1 | Intra-Utility 2 | Leveraging 3 | Combined (B+C+D) | Online | Paper | Phone | Capitation | Combined (F+G+H+I)
January | 3751 | 216 | 0 | 3967 | 5159 | 4912 | 5473 | 9 | 15553 | 19520 | 16742 | 12718 | 0 | 29460 | 10416 | 3 | 725 | 10441 | 21585 | 48980 | -2065 | 1203474 | 1337092 | 90.01%
February | 4118 | 231 | 0 | 4349 | 5641 | 3889 | 5200 | 36 | 14766 | 19115 | 14185 | 12703 | 0 | 26888 | 9436 | 26 | 612 | 7205 | 17279 | 46003 | 1836 | 1205310 | 1337092 | 90.14%
March | 4800 | 164 | 0 | 4964 | 5561 | 2509 | 5473 | 16 | 13559 | 18523 | 10215 | 16165 | 0 | 26380 | 8326 | 18 | 466 | 10899 | 19709 | 44903 | -1186 | 1204124 | 1337092 | 90.06%
April | 3951 | 311 | 0 | 4262 | 4571 | 2605 | 4493 | 28 | 11697 | 15959 | 9854 | 13652 | 0 | 23506 | 8791 | 120 | 457 | 18328 | 27696 | 39465 | -11737 | 1192387 | 1337092 | 89.18%
May | 3936 | 222 | 0 | 4158 | 4476 | 6658 | 3796 | 47 | 14977 | 19135 | 13253 | 14199 | 0 | 27452 | 8569 | 168 | 539 | 10705 | 19981 | 46587 | -846 | 1191541 | 1337092 | 89.11%
June | 3212 | 243 | 0 | 3455 | 4706 | 6889 | 3770 | 121 | 15486 | 18941 | 11925 | 12616 | 0 | 24541 | 10334 | 98 | 528 | 10101 | 21061 | 43482 | -2120 | 1189421 | 1337092 | 88.96%
July
August
September
October
November
December
YTD Total | 23768 | 1387 | 0 | 25155 | 30114 | 27462 | 28205 | 257 | 86038 | 111193 | 76174 | 82053 | 0 | 158227 | 55872 | 433 | 3327 | 67679 | 127311 | 269420 | -16118 | 1189421 | 1337092 | 88.96%
1 Enrollments via data sharing between the IOUs.
2 Enrollments via data sharing between departments and/or programs within the utility.
3 Enrollments via data sharing with programs outside the IOU that serve low-income customers.
[4] Recertification results are tied to the month initiated. Therefore, recertification results may be pending due to the time permitted for a participant to respond.
[5] Numbers are not tied to month initiated but are operational and reflect customer enrollment status changes that were triggered that month; these numbers differ from the tied to month initiated numbers provided elsewhere in this report.
[6] No response includes no response to both Recertification and Verification.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## CARE Table 3A _3B
CARE Table 3A - Post-Enrollment Verification Results (Model)
Southern California Edison
Through June 2019
Month | Total CARE Households Enrolled | Households Requested to Verify | % of CARE Enrolled Requested to Verify Total | CARE Households De-enrolled (Due to no response) | CARE Households De-enrolled (Verified as Ineligible) [1] | Total Households De-enrolled [2] | % De-enrolled through Post Enrollment Verification | % of Total CARE Households De-enrolled
January | 1203474 | 5273 | 0.4381% | 3617 | 84 | 3701 | 70.19% | 0.3075%
February | 1205310 | 43 | 0.003568% | 17 | 0 | 17 | 39.53% | 0.00141%
March | 1204124 | 6152 | 0.5109% | 2672 | 95 | 2767 | 44.98% | 0.2298%
April | 1192387 | 7089 | 0.5945% | 41 | 69 | 110 | 1.552% | 0.009225%
May | 1191541 | 8285 | 0.6953% | 31 | 46 | 77 | 0.9294% | 0.006462%
June | 1189421 | 7976 | 0.6706% | 23 | 0 | 23 | 0.2884% | 0.001934%
July
August
September
October
November
December
YTD Total | 1189421 | 34818 | 2.927% | 6401 | 294 | 6695 | 19.23% | 0.5629%
[1] Includes customers verified as over income or who requested to be de-enrolled.
[2] Verification results are tied to the month initiated. Therefore, verification results may be pending due to the time permitted for a participant to respond.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.
CARE Table 3B Post-Enrollment Verification Results (Electric only High Usage)
Southern California Edison
Through June 2019
Month | Total CARE Households Enrolled | Households Requested to Verify 1 | % of CARE Enrolled Requested to Verify Total | CARE Households De-enrolled (Due to no response) | CARE Households De-enrolled (Verified as Ineligible) 2 | Total Households De-enrolled 3 | % De-enrolled through HUV Post Enrollment Verification | % of Total CARE Households De-enrolled
January | 1203474 | 3126 | 0.2597% | 2979 | 9 | 2988 | 95.59% | 0.2483%
February | 1205310 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
March | 1204124 | 10684 | 0.8873% | 9815 | 95 | 9910 | 92.76% | 0.823%
April | 1192387 | 1430 | 0.1199% | 1207 | 12 | 1219 | 85.24% | 0.1022%
May | 1191541 | 189 | 0.01586% | 0 | 0 | 0 | 0% | 0%
June | 1189421 | 467 | 0.03926% | 0 | 0 | 0 | 0% | 0%
July
August
September
October
November
December
YTD Total | 1189421 | 15896 | 1.336% | 14001 | 116 | 14117 | 88.81% | 1.187%
1 Includes all participants who were selected for high usage verification process. Closed accounts will not be tracked in Ineligible or De-enrolled data.
2 Includes customers verified as over income, who requested to be de-enrolled, did not reduce usage, or did not agree to be weatherized.
3 Verification results are tied to the month initiated and the high usage verification process allows customers 90 days to respond to the verification process. Each utility may have a different de-enrollment date due to billing cycle or other contributing factors.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## CARE Table 4
CARE Table 4 - CARE Self-Certification and Self-Recertification Applications 1
Southern California Edison
Through June 2019
| Provided [2] | Received | Approved | Denied [4] | Pending/Never Completed [5] | Duplicates
Total (Y-T-D) | 517448.2 | 419758 | 252842 | 43143 | 69786 | 123773
Percentage [3] | N/A | 100% | 60.24% | 10.28% | N/A | 29.49%
1 Includes sub-metered customers.
[2] Includes number of applications SCE provided for all direct mailing campaigns, customer calls made to the call center, and other outreach methods. Because there are other means by which customers obtain applications which are not counted, this number is only an approximation.
[3] Percent of received applications.
[4] Includes all applications received and not approved.
[5] Includes pending recertification responses.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## CARE Table 5
CARE Table 5 - Enrollment by County
Southern California Edison
Through June 2019
County | Estimated Eligible Households* |  |  | Total Households Enrolled |  |  | Penetration Rate
| Urban | Rural | Total | Urban | Rural | Total | Urban | Rural | Total
Fresno | 520 | 0 | 520 | 39 | 0 | 39 | 7.5% | 0% | 7.5%
Imperial | 0 | 185 | 185 | 0 | 66 | 59 | 0% | 35.68% | 31.89%
Inyo | 4.5915 | 1269.4085 | 1274 | 0 | 961 | 961 | 0% | 75.7% | 75.43%
Kern | 13028.4278 | 17208.5722 | 30237 | 8647 | 13759 | 22303 | 66.37% | 79.95% | 73.76%
Kings | 0 | 8346 | 8346 | 0 | 8874 | 8798 | 0% | 106.3% | 105.4%
Los Angeles | 534621.0574 | 3059.9426 | 537681 | 497727 | 1530 | 498048 | 93.1% | 50% | 92.63%
Madera | 3 | 0 | 3 | 0 | 0 | 0 | 0% | 0% | 0%
Mono | 0.35213 | 1564.6479 | 1565 | 0 | 745 | 743 | 0% | 47.61% | 47.48%
Orange | 199928.6001 | 0.39986 | 199929 | 149560 |  | 148914 | 74.81% | 0% | 74.48%
Riverside | 97340.7957 | 92884.2043 | 190225 | 78884 | 89231 | 166323 | 81.04% | 96.07% | 87.43%
San Bernardino | 188658.0615 | 36340.9385 | 224999 | 184307 | 36450 | 219595 | 97.69% | 100.3% | 97.6%
San Diego | 0 | 1 | 1 | 0 | 1 | 1 | 0% | 100% | 100%
Santa Barbara | 17543 | 0 | 17543 | 9396 |  | 9346 | 53.56% | 0% | 53.27%
Tulare | 13396.9256 | 45559.0744 | 58956 | 12168 | 43170 | 55298 | 90.83% | 94.76% | 93.8%
Ventura | 63059.5826 | 2568.4174 | 65628 | 52145 | 1761 | 53666 | 82.69% | 68.56% | 81.77%
Total | 1128104.3944 | 208987.6056 | 1337092 | 992873 | 196548 | 1189421 | 88.01% | 94.05% | 88.96%
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.
* Estimated eligible households is updated using Athens Research dataset provided in March 2019.
`

## CARE Table 6
CARE Table 6 - Recertification Results
Southern California Edison
Through June 2019
Month | Total CARE Households | Households Requested to Recertify 1 | % of Households Total (C/B) | Households Recertified 2 | Households De-enrolled 3 | Recertification Rate % 4 (E/C) | % of Total Households De-enrolled (F/B)
January | 1203474 | 22267 | 1.85% | 12995 | 9120 | 58.36% | 0.7578%
February | 1205310 | 17512 | 1.453% | 9977 | 7394 | 56.97% | 0.6135%
March | 1204124 | 21519 | 1.787% | 11881 | 8138 | 55.21% | 0.6758%
April | 1192387 | 20311 | 1.703% | 10245 | 1433 | 50.44% | 0.1202%
May | 1191541 | 24102 | 2.023% | 8910 | 956 | 36.97% | 0.08023%
June | 1189421 | 23775 | 1.999% | 3336 | 504 | 14.03% | 0.04237%
July
August
September
October
November
December
YTD | 1189421 | 129486 | 10.89% | 57344 | 27545 | 44.29% | 2.316%
1 Excludes count of customers recertified through the probability model.
2 Recertification results are tied to the month initiated and the recertification process allows customers 90 days to respond to the recertification request. Results may be pending due to the time permitted for a participant to respond.
3 Includes customers who did not respond or who requested to be de-enrolled.
4 Percentage of customers recertified compared to the total participants requested to recertify in that month.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## CARE Table 7
CARE Table 7 - Capitation Contractors1
Southern California Edison
Through June 2019
Contractor [1] | Contractor Type |  |  |  | Total Enrollments
(Check one or more if applicable)
| Private | CBO | WMDVBE | LIHEAP | Current Month | Year-to-Date [2]
ALPHA ENTERPRISES |  | x |  |  | 0 | 0
APAC SERVICE CENTER | x |  |  |  | 0 | 7
ARMENIAN RELIEF SOCIETY | x |  |  |  | 0 | 0
ASIAN AMERICAN DRUG ABUSE PROG | x |  |  |  | 1 | 6
ASIAN AMERICAN RESOURCE CENTER | x |  | x |  | 0 | 0
ASIAN YOUTH CENTER | x |  |  |  | 0 | 0
BEST PARTNERS | x |  |  |  | 107 | 185
DELHI CENTER | x |  |  |  | 0 | 7
BETHEL BAPTIST CHURCH | x |  |  |  | 0 | 0
BISHOP PAIUTE TRIBE | x |  |  |  | 0 | 0
C.O.R. COMM DEVELOPMENT CORP | x |  |  |  | 0 | 0
CAREGIVERS VOLUNTEERS ELDERLY |  | x |  |  | 0 | 0
CHINESE CHRISTIAN HERALD CRUS. | x |  |  |  | 0 | 0
CHINO NEIGHBORHOOD HOUSE |  | x |  |  | 0 | 0
CITIHOUSING REAL ESTATE SERVIC |  | x |  |  | 0 | 0
CITY IMPACT | x |  |  |  | 0 | 0
CITY OF BEAUMONT SENIOR CENTER |  | x | x |  | 0 | 0
COMMUNITY HEALTH INITIATIVE of OC (AKA: Volunteer Center of Greater Orange County dba OneOC ) |  | x |  |  | 0 | 0
CORONA NORCO FAMILY YMCA | x |  |  |  | 0 | 0
DESERT ARC | x |  |  |  | 0 | 0
DESERT MANNA MINISTRIES INC | x |  |  |  | 0 | 0
DISABLED RESOURCES CTR, INC |  | x | x |  | 2 | 3
EL CONCILIO DEL CONDADO DE | x |  | x |  | 0 | 0
FAMILY SVC ASSOC OF REDLANDS | x |  |  |  | 0 | 0
FOOD SHARE | x |  |  |  | 0 | 0
GO THE CALENDAR |  | x |  |  | 0 | 0
HELP OF OJAI, INC. | x |  |  |  | 0 | 0
HOUSING AUTHORITY OF KINGS CO | x |  | x |  | 0 | 0
KERNVILLE UNION SCHOOL DISTRIC | x |  |  |  | 0 | 0
KINGS COMMUNTITY ACTION ORG | x |  |  |  | 0 | 0
KINGS CTY COMMISSION ON AGING | x |  |  |  | 0 | 0
LA COUNTY HOUSING AUTHORITY |  | x |  |  | 0 | 0
LEAGUE OF CALIF HOMEOWNERS | x |  |  |  | 0 | 0
LTSC COMM. DEVEL. CORP | x |  |  |  | 2 | 5
MENIFEE VALLEY CHAMBER |  | x |  |  | 0 | 0
MEXICAN AMERICAN OPPORTUNITY |  | x | x |  | 0 | 0
MTN COMM FAM RESOURCE CNTR | x |  |  |  | 0 | 5
NEW GREATER CIR. MISSION, INC | x |  |  |  | 0 | 0
NEW HOPE VILLAGE, INC | x |  |  |  | 0 | 1
NEW HORIZONS CAREGIVERS GROUP |  | x |  |  | 0 | 2
OCCC | x |  |  |  | 0 | 1
OPERATION GRACE | x |  |  |  | 0 | 0
OUR COMMUNITY WORKS | x |  |  |  | 7 | 23
PACIFIC ISLANDER HLTH (PIHP) | x |  |  |  | 0 | 0
PACIFIC PRIDE FOUNDATION | x |  |  |  | 0 | 0
RIVERSIDE DEPT COMM ACTION |  | x | x | x | 2 | 12
SALVATION ARMY SANTA FE SPGS | x |  |  |  | 0 | 0
SALVATION ARMY VISALIA CORPS | x |  |  |  | 0 | 0
SANTA ANITA FAMILY SERVICE | x |  |  |  | 0 | 0
SENIOR ADVOCATES OF THE DESERT | x |  |  |  | 0 | 0
SHARE OUR SELVES | x |  |  |  | 0 | 0
SMILES FOR SENIORS FOUND. | x |  |  |  | 0 | 0
SOUTHEAST CITIES SERVICE CTR. |  | x |  |  | 0 | 0
SOUTHEAST COMMUNITY DEVELOPMEN | x |  |  |  | 0 | 0
ST VINCENT DE PAUL |  | x |  |  | 0 | 0
THE CAMBODIAN FAMILY | x |  |  |  | 0 | 0
UNITED CAMBODIAN COMMUNITY INC |  | x |  |  | 0 | 0
VICTOR VALLEY COMM SVC COUNCIL | x |  |  |  | 0 | 0
VIETNAMESE COMMUNITY OF OC INC | x |  |  |  | 0 | 0
VOLUTNEERS OF EAST LOS ANGELES | x |  | x |  | 0 | 0
XFINITI SOLUTIONS, LLC |  | x |  |  | 0 | 0
Total Enrollments |  |  |  |  | 121 | 257
[1] All capitation contractors with current contracts are listed regardless of whether they have signed up customers or submitted invoices this year.
[2] Numbers reflect customers that have been placed on the rate YTD. Capitation payments may lag by a month or more depending on when SCE is invoiced by the contractors.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## CARE Table 8
CARE Table 8 - Households as of Month-End
Southern California Edison
Through June 2019
Month | Gas and Electric | Gas Only | Electric Only | Total | Eligible Households | Penetration | % Change | Total Residential Accounts [1]
January |  |  | 1203474 | 1203474 | 1337092 | 90.01% | 0% | 4432776
February |  |  | 1205310 | 1205310 | 1337092 | 90.14% | 0% | 4432049
March |  |  | 1204124 | 1204124 | 1337092 | 90.06% | 0% | 4432454
April |  |  | 1192387 | 1192387 | 1337092 | 89.18% | 0% | 4432454
May |  |  | 1191541 | 1191541 | 1337092 | 89.11% | 0% | 4437452
June |  |  | 1189421 | 1189421 | 1337092 | 88.96% | 0% | 4435897
July
August
September
October
November
December
YTD |  |  | 1189421 | 1189421 | 1337092 | 88.96% | 0% | 4435897
[1] Data represents total residential electric and gas households. This includes submetered households.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## CARE Table 9
CARE Program Table 9 - Expenditures for Pilots/CHANGES Program
Southern California Edison
Through June 2019
2018 | Authorized 2018 Budget | Current Month Expenses | Expenses Since Jan. 1, 2018 | % of 2018 Budget Expensed
Pilots
CHANGES Program | 525000 | 120203.3 | 223198.68 | 42.51%
Total | 525000 | 120203.3 | 223198.68 | 42.51%
[1] Decision 15-12-047 transitioned from CHANGES pilot to CHANGES program and funding for the effort is captured herein.
Note: Any required corrections/adjustments are reported herein and supersede results reported in prior months and may reflect YTD adjustments.

## CARE Table 10
Per Ravinder Mangat from the CPUC, table 10 is temporarily suspended.
CARE Table 10 CHANGES One-On-One Customer Assistance Sessions
Southern California Edison
Reporting Period May 1, 2018, through May 31, 2018
Date[3] | CHANGES Participants’ self-identified language of preference | Description of the session content identifying service provided (e.g. utility bill assistance, utility bill dispute resolution, and other energy related issues)[2] | Description of each contact made with that customer’s utility until a solution is reached. | If on CARE, Enter How Initially Enrolled |  | Number of Enrollment through CHANGES CBOs' Assistance Confirmed by IOU |  |  | Customer Receiving Assistance with Bill Payment Plans (initiated or modified) by the CHANGES CBOs. |  |  | Customer Receiving Assistance with Utility Bill Disputes, including bill modification, by the CHANGES CBOs. |  |  | Calls to Dedicated 800 # Recorded by IOU [1]
|  |  |  | # | How Enrolled | CARE | FERA | Medical Baseline | # | Dedicated Toll-Free Number Used |  | # | Dedicated Toll-Free Number Used
[10 empty] | 1 = Yes 0 = No | Reason 800 # Not Used |  | 1 = Yes 0 = No | Reason 800 # Not Used
2018-05-02 | Chinese/Cantonese | Energy Assistance Fund Application Educated on Energy Efficiency/ Conservation Educated on Energy Assistance Programs | Not applicable | 1 | Recertification and Verification Processing | 0 | 0 | 1 | 1 | 0 | Not Applicable | 1 | 0 | Not Applicable
2018-05-23 | Vietnamese | HEAP/LiHeap Application Assistance Educated on Energy Assistance Programs | Not applicable | 1 | Data Sharing | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-22 | Korean | HEAP/LiHeap Application Assistance | Not applicable | 1 | Data Sharing | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-23 | Korean | HEAP/LiHeap Application Assistance | Not applicable | 1 | Recertification and Verification Processing | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 0 | 1 | Not Applicable
2018-05-23 | Spanish | HEAP/LiHeap Application Assistance Set Up/Change Payment Plan | Not applicable | 1 | Internet Enrollments | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-16 | Chinese/Cantonese | Energy Assistance Fund Application Educated on Energy Efficiency/ Conservation | Not applicable | 1 | VRU Enrollments | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-11 | Spanish | Medical Baseline Application Assistance Educated on Medical Baseline | Not applicable | 1 | Internet Enrollments | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-03 | Spanish | Educated on CARE/FERA Changes to Account | Not applicable | 1 | Capitation Agency | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 1 | 1 | Not Applicable
2018-05-15 | Vietnamese | HEAP/LiHeap Application Assistance Bill Education Educated on Energy Assistance Programs | Not applicable | 1 | Capitation Agency | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-02 | Spanish | Educated on CARE/FERA Changes to Account | Not applicable | 1 | Capitation Agency | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-07 | Vietnamese | HEAP/LiHeap Application Assistance Bill Education Educated on Energy Assistance Programs | Not applicable | 1 | Special Projects | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-22 | Vietnamese | HEAP/LiHeap Application Assistance Bill Education Educated on Energy Assistance Programs | Not applicable | 1 | Capitation Agency | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-04 | Spanish | ESAP Application Assistance | Not applicable | 1 | Internet Enrollments | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-03 | English | Set Up/Change Payment Plan | Not applicable | 1 | Capitation Agency | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-18 | Chinese/Cantonese | HEAP/LiHeap Application Assistance Educated on Energy Efficiency/ Conservation | Not applicable | 1 | Call Center | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-10 | Samoan | Set Up/Change Payment Plan | Not applicable | 0 | Not Applicable | 0 | 0 | 0 | 1 | 1 | Not Applicable | 0 | 0 | Not Applicable
2018-05-08 | English | Set Up/Change Payment Extension | Not applicable | 0 | Not Applicable | 0 | 0 | 0 | 1 | 1 | Not Applicable | 0 | 0 | Not Applicable
2018-05-14 | Vietnamese | HEAP/LiHeap Application Assistance | Not applicable | 1 | Capitation Agency | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-22 | English | Energy Assistance Fund Application Educated on Energy Efficiency/ Conservation | Not applicable | 1 | Capitation Agency | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 1 | 0 | Not Applicable
0 | 0 |  | Not applicable | 1 | Call Center | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-14 | Spanish | Set Up/Change Payment Extension Set Up/Change Payment Plan | Not applicable | 1 | Call Center | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-16 | Spanish | Changes to Account | Not applicable | 1 | Call Center | 0 | 0 | 0 | 1 | 1 | Not Applicable | 0 | 0 | Not Applicable
2018-05-30 | Spanish | Set Up/Change Payment Extension | Not applicable | 1 | Capitation Agency | 0 | 0 | 0 | 0 | 1 | Not Applicable | 0 | 0 | Not Applicable
2018-05-02 | Chinese/Cantonese | HEAP/LiHeap Application Assistance Educated on Energy Efficiency/ Conservation | Not applicable | 1 | Call Center | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 1 | 0 | Not Applicable
2018-05-14 | Korean | HEAP/LiHeap Application Assistance | Not applicable | 0 | Not Applicable | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 0 | 0 | Not Applicable
0 | 0 |  | Not applicable | 1 | Special Projects | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-22 | Korean | HEAP/LiHeap Application Assistance | Not applicable | 1 | Special Projects | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-30 | Vietnamese | HEAP/LiHeap Application Assistance | Not applicable | 1 | Call Center | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 1 | 0 | Not Applicable
2018-05-14 | Spanish | ESAP Application Assistance | Not applicable | 1 | Call Center | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-14 | Spanish | Medical Baseline Application Assistance Educated on Medical Baseline | Not applicable | 1 | Call Center | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-15 | Chinese/Cantonese | Energy Assistance Fund Application Educated on Energy Efficiency/ Conservation | Not applicable | 1 | Capitation Agency | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 1 | 0 | Not Applicable
2018-05-18 | Spanish | ESAP Application Assistance Educated on CARE/FERA | Not applicable | 1 | Internet Enrollments | 0 | 0 | 0 | 0 | 1 | Not Applicable | 0 | 0 | Not Applicable
2018-05-23 | Spanish | ESAP Application Assistance Set Up/Change Payment Extension Set Up/Change Payment Plan | Not applicable | 1 | Internet Enrollments | 0 | 0 | 0 | 0 | 1 | Not Applicable | 0 | 0 | Not Applicable
2018-05-09 | Spanish | HEAP/LiHeap Application Assistance | Not applicable | 1 | Call Center | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-15 | Spanish | Set Up/Change Payment Extension Set Up/Change Payment Plan | Not applicable | 1 | Call Center | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-21 | Vietnamese | HEAP/LiHeap Application Assistance | Not applicable | 0 | Not Applicable | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-25 | Spanish | Set Up/Change Payment Plan | Not applicable | 1 | Call Center | 0 | 0 | 0 | 0 | 1 | Not Applicable | 0 | 0 | Not Applicable
2018-05-25 | Spanish | ESAP Application Assistance | Not applicable | 1 | Capitation Agency | 0 | 0 | 0 | 0 | 1 | Not Applicable | 0 | 0 | Not Applicable
2018-05-16 | Spanish | Changes to Account | Not applicable | 1 | Call Center | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-09 | Spanish | ESAP Application Assistance | Not applicable | 1 | Call Center | 0 | 0 | 1 | 0 | 0 | Meeting with client. | 1 | 0 | Not Applicable
2018-05-10 | Vietnamese | HEAP/LiHeap Application Assistance Educated on Avoiding Disconnection Educated on Energy Assistance Programs | Not applicable | 1 | Data sharing | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-04-30 | English | Set Up/Change Payment Plan | Not applicable | 1 | VRU Enrollments | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-01 | Chinese/Cantonese | Energy Assistance Fund Application Educated on Energy Efficiency/ Conservation Educated on Energy Assistance Programs | Not applicable | 0 | Not Applicable | 0 | 0 | 0 | 1 |  | Not Applicable | 0 | 1 | Not Applicable
2018-05-01 | English | HEAP/LiHeap Application Assistance | Not applicable | 0 | Not Applicable | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-08 | English | Changes to Account | Not applicable | 1 | Special Projects | 0 | 0 | 0 | 1 |  |  | 0 | 1 | Not Applicable
2018-04-17 | English | Energy Assistance Fund Application | Not applicable | 0 | Not Applicable | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-03 | Chinese/Cantonese | HEAP/LiHeap Application Assistance Educated on Energy Efficiency/ Conservation | Not applicable | 1 | Call Center | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-25 | English | Medical Baseline Application Assistance Educated on Medical Baseline | Not applicable | 0 | Not Applicable | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-04 | Vietnamese | HEAP/LiHeap Application Assistance | Not applicable | 1 | Capitation Agency | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-10 | Chinese/Cantonese | HEAP/LiHeap Application Assistance Educated on Energy Efficiency/ Conservation | Not applicable | 0 | Not Applicable | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 1 | 0 | Not Applicable
2018-05-25 | Chinese/Cantonese | HEAP/LiHeap Application Assistance Educated on Energy Efficiency/ Conservation | Not applicable | 1 | VRU Enrollments | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-04 | Chinese/Cantonese | HEAP/LiHeap Application Assistance Educated on Energy Efficiency/ Conservation | Not applicable | 1 | Call Center | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-05-03 | Vietnamese | HEAP/LiHeap Application Assistance | Not applicable | 1 | Call Center | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not Applicable
2018-04-25 | English | HEAP/LiHeap Application Assistance | Not applicable | 1 | Other Source | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 0 | 0 | Not applicable
2018-04-02 | Mandarin | Energy Assistance Fund Application | Not applicable | 1 | Special Projects | 0 | 0 | 0 | 1 | 0 | Meeting with client. | 1 | 0 | Not applicable
2018-04-10 | Spanish | Medical Baseline Application Assistance | Not applicable | 1 | Internet Enrollments | 0 | 0 | 0 | 0 | 0 | Meeting with client. | 0 | 0 | Not applicable
2018-04-27 | Spanish | Changes to Account | Not applicable | 1 | Internet Enrollments | 0 | 0 | 0 | 0 | 1 | Not Applicable | 0 | 0 | Not applicable
Current Month Total |  |  |  | 48 |  | 0 | 0 | 2 | 20 | 9 |  | 9 | 4 |  | 26
Year-to-Date Total |  |  |  | 578 |  | 9 | 0 | 21 | 257 | 40 |  | 88 | 22 |  | 73
[1] Total calls placed to 800# recorded by SCE from May 1, 2018, through May 31, 2018, is 26. Data on calls per each one-on-one session not available.
[2] For column C, this data was provided by CHANGES contractor, Self Help for the Elderly, via CSID. This table was edited and reformatted from its original version in order to have a more consistent appearance and format with existing SCE tables.
[3] Dates listed are one-on-one case open dates as provided by CHANGES contractor. Dates do not necessarily coincide with the date of the session.

## CARE Table 11
CARE Table 11 CHANGES Group Customer Assistance Sessions₍₂₎₍₃₎
Southern California Edison
Reporting Period May 1, 2018, through July 31, 2018
Date | Session Language | Description of Service Provided (e.g. utility bill assistance, utility bill dispute resolution, and other energy related issues) | Sessions Logistics
|  |  | # of Sessions | Length₍₁₎ (Hours) | Number of Attendees (4) | Description of Information / Literature Provided
N/A | Armenian | Avoiding Disconnection | 6 | 0.5 | 42 | N/A | 134
N/A | Cantonese | Avoiding Disconnection | 1 | 0.5 | 17 | N/A | 74
N/A | English | Avoiding Disconnection | 2 | 0.5 | 8 | N/A | 50
N/A | Japanese | Avoiding Disconnection | 1 | 0.5 | 1 | N/A | 14
N/A | Korean | Avoiding Disconnection | 1 | 0.5 | 16 | N/A | 40
N/A | Mandarin | Avoiding Disconnection | 1 | 0.5 | 4 | N/A | 36
N/A | Spanish | Avoiding Disconnection | 1 | 0.5 | 2 | N/A | 121
N/A | Vietnamese | Avoiding Disconnection | 2 | 0.5 | 31 | N/A | 137
N/A | Cantonese | CARE/FERA and Other Assistance Programs | 1 | 0.5 | 1 | N/A | 49
N/A | English | CARE/FERA and Other Assistance Programs | 8 | 0.5 | 29 | N/A | 10
N/A | Japanese | CARE/FERA and Other Assistance Program | 1 | 0.5 | 1 | N/A | 35
N/A | Korean | CARE/FERA and Other Assistance Programs | 4 | 0.5 | 157 | N/A | 1
N/A | Mandarin | CARE/FERA and Other Assistance Programs | 3 | 0.5 | 6 | N/A | 12
N/A | Spanish | CARE/FERA and Other Assistance Programs | 8 | 0.5 | 64 | N/A | 236
N/A | Vietnamese | CARE/FERA and Other Assistance Program | 2 | 0.5 | 31 | N/A | 22
N/A | Armenian | Electric and Natural Gas Safety | 6 | 0.5 | 46 | N/A | 6
N/A | Cantonese | Electric and Natural Gas Safety | 2 | 0.5 | 24 | N/A | 123
N/A | English | Electric and Natural Gas Safety | 5 | 0.5 | 18 | N/A | 117
N/A | Korean | Electric and Natural Gas Safety | 1 | 0.5 | 8 | N/A | 33
N/A | Mandarin | Electric and Natural Gas Safety | 3 | 0.5 | 7 | N/A | 2
N/A | Spanish | Electric and Natural Gas Safety | 6 | 0.5 | 46 | N/A | 93
N/A | Tagalog | Electric and Natural Gas Safety | 3 | 0.5 | 26 | N/A | 55
N/A | Vietnamese | Electric and Natural Gas Safety | 1 | 0.5 | 8 | N/A | 28
N/A | Armenian | Energy Conservation | 6 | 0.5 | 37 | N/A | 46
N/A | Cantonese | Energy Conservation | 2 | 0.5 | 23 | N/A | 151
N/A | English | Energy Conservation | 2 | 0.5 | 7 | N/A | 75
N/A | Mandarin | Energy Conservation | 3 | 0.5 | 10 | N/A | 36
N/A | Spanish | Energy Conservation | 3 | 0.5 | 15 | N/A | 33
N/A | Cambodian | Gas Aggregation | 1 | 0.5 | 8 | Gas Aggregation Handout | 74
N/A | English | Gas Aggregation | 1 | 0.5 | 2 | Gas Aggregation Handout | 54
N/A | Mandarin | Gas Aggregation | 1 | 0.5 | 1 | Gas Aggregation Handout | 28
N/A | Spanish | Gas Aggregation | 3 | 0.5 | 32 | Gas Aggregation Handout | 20
N/A | Spanish | High Energy Use | 1 | 0.5 | 18 | High Use Handout | 139
N/A | Cantonese | Level Pay Plan | 1 | 0.5 | 14 | N/A | 28
N/A | English | Level Pay Plan | 1 | 0.5 | 7 | N/A | 37
N/A | Mandarin | Level Pay Plan | 1 | 0.5 | 3 | N/A | 53
N/A | Tagalog | Level Pay Plan | 1 | 0.5 | 8 | N/A | 7
N/A | Vietnamese | Level Pay Plan | 1 | 0.5 | 17 | N/A | 4
N/A | Arabic | Understanding Your Bill | 1 | 0.5 | 5 | N/A | 14
N/A | Armenian | Understanding Your Bill | 2 | 0.5 | 7 | N/A | 20
N/A | Cantonese | Understanding Your Bill | 1 | 0.5 | 15 | N/A | 330
N/A | English | Understanding Your Bill | 3 | 0.5 | 10 | N/A | 30
N/A | Japanese | Understanding Your Bill | 2 | 0.5 | 17 | N/A | 21
N/A | Korean | Understanding Your Bill | 3 | 0.5 | 25 | N/A | 14
N/A | Mandarin | Understanding Your Bill | 2 | 0.5 | 4 | N/A | 6
N/A | Spanish | Understanding Your Bill | 5 | 0.5 | 55 | N/A | 14
N/A | Tagalog | Understanding Your Bill | 2 | 0.5 | 26 | N/A | 75
N/A | Vietnamese | Understanding Your Bill | 2 | 0.5 | 35 | N/A | 21
Current Quarter Total |  |  | 120 |  | 994 |  | 42
Year-to-Date |  |  | 1330 |  | 12690 |  | 17
18
[1] Contractor states all sessions at least 30 minutes | [6 empty] | 36
[2] This table was provided by CHANGES contractor, Self Help for the Elderly, via CSID. This table was edited and reformatted from its original versions in order to have a more consistent appearance and format with existing SCE tables. | [6 empty] | 62
[3] The numbers provided by the CHANGES contractor are for SCE and SoCal Gas combined, due to the combined service territory. | [6 empty] | 2
[4] On the Consumer Education Topic addendum of the Quarterly CHANGES Data Report of August 2018-October 2018, the number of attendees for: the Avoiding Disconnection course add up to 121, not the 119 shown on the report; CARE / FERA & Other Assistance Programs classes add up to 289, not 287 as shown on the report; Electric and Natural Gas Safety classes add up to 183, not 182 as shown on the report; Energy Conservation classes add up to 92, not 91 as shown on the report; Understanding Your Bill classes add up to 199, not 197 as shown on the report. Thus, the total shown on this table does not match the total on the Quarterly CHANGES Data Report of August 2018-October 2018.